## Slide 1
December 3, 2013
2013 Year End Support Pack Project
Steering Committee
Go/no-go

## Slide 2: Issues
Is it worth it?
Well, yes …
  We can jump to RT for details: https://help.mit.edu/
Phases Issues were identified in … |  |  |  | 
(as of 12/2/13) |  |  |  | 
Issue type | Unit | SIT |  | Total
Required an SAP fix | 12 | 11 |  | 23
Required an MIT fix | 10 | 9 |  | 19
Infrastructure Related | 5 | 17 |  | 22
User/Data Error | 0 | 5 |  | 5
Duplicate | 1 | 7 |  | 8
Production Issue | 3 | 6 |  | 9
Totals | 31 | 55 |  | 86

## Slide 3: Issues (cont.)
How does it compare to prior years?
 | 2010 | 2011 | 2012 | 2013
Issues | 64 | 41 | 54 | 86
SAP fix required | 3 | 8 | 9 | 23
MIT fix required | 23 | 17 | 17 | 19
Total fixes required | 26 | 25 | 26 | 42

## Slide 4: Issues (cont)
  Identified 86 issues/ resolved 82/ balance of 4 – in process
  SAP issues of particular concern
    EH&S Supervisor Injury Report – source for OSHA reporting (resolved)
    Tax File Download for transmission (resolved)
    Finance Summary and Detail report (requires an MIT fix )
      9 Reports in all
      9 Complete
    ITS issue (resolved)
    Webdynpro running in Firefox issue (resolved – worked through the weekend)
    Let’s jump to RT to review open issues …

## Slide 5: Recommendation
Move forward with the upgrade this weekend
  ERP
  Portal
  GRC
  ADS (hold)

## Slide 6: Cutover
Preparation work
System Isolation
Support Pack Application
Post Upgrade Processes (conversions, validations)
Go-live
  Let’s jump to the project wiki’s Cutover Plan page and take a look at the plan …

## Slide 7: Next Steps
12/4/2013 Transport Review (2:00pm)
12/4/2013 Action Log Review (3:00pm)
12/6/2013 (5:00pm) - 12/8/2013 Go-live weekend!
Meaning … we’ll have to execute a cutover plan!!