## Sheet1
SAP - Consolidated Action Log
This document is used by IS&T and Business Process Owners as a guide to validate SAP systems after a database copy, infrastructure update and version upgrade. | [8 empty] | Performed in Environment? | [23 empty] | Dependencies or Timing Issues | Notes
Task # | User/Resp | Area | Dev/ Config / Trx. | DB Copy | Infra Update | Upgrade | R3 Auth | Description | SF3 Refresh |  | SF3 Post SP Application |  | SF6 Refresh |  | SF2 Post SP |  | SF2 Refresh |  | SH2 Refresh |  | SH2 Post SP Application |  | PS1 Post SP Application |  | SH1 Refresh |  | SH3 |  | SF8 update |  | SE1 Refresh
[9 empty] | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status
1 | Ron Parker | Email Notification | SE38 | Yes | Yes | Yes |  | Program ZBRSMAIL provides a mechanism to modify, replace, append, or write to tables Zemctrl and Zehcat. It is also possible to delete all of the rows of either of the two tables. These tables are used in the email redirection/distribution process. (Download values in ZEHCAT and ZEMCTRL tables) | Yes | complete | No | n/a | Yes |  | No | n/a | Yes |  | Yes |  | No | n/a | No | n/a | Yes |  | Yes |  | Yes |  | Yes |  |  | Pre-refresh settings exported and then import after the refresh.
2 | Ron Parker | Email Notification |  | Yes | Yes | Yes |  | Reset table settings for Z_SENDMAIL : 1. delete all entries from ZEMCTRL. 2. replace the contents of ZEHCAT with two rows: HNCAT=<space><space>, CMODE=X, ACTION=X, All other fields=<space>; HNCAT=++, CMODE=X, ACTION=X, All other fields=<space> | Yes | complete | No | n/a | Yes |  | No | n/a | Yes |  | Yes |  | No | n/a | No | n/a | Yes |  | Yes |  | Yes |  | Yes |  |  | Pre-refresh settings exported and then import after the refresh.
3 | Ron Parker | Email Notification | Config | Yes | Yes | Yes |  | Redirect e-mail notifications. Transaction SE30 Call View Maintenance. Table: ZEHCAT E-mail control table - handling categories. Action: Redirect Emailto: user@mit.edu or Action: Cancel. | Yes | complete | No | n/a | Yes |  | No | n/a | Yes |  | Yes |  | No | n/a | No | n/a | Yes |  | Yes |  | Yes |  | Yes |  |  | Pre-refresh settings exported and then import after the refresh.
4 | Ron Parker | ITS | SICF |  |  |  |  | Activate /default_host/sap/public/bc/its/mimes | validate | complete | validate | complete | validate |  | validate | complete | validate |  | validate |  | validate |  | validate |  | validate |  | validate |  | validate |  | validate
5 | Ron Parker | ITS | SICF |  |  |  |  | 1. SICF 2. /default_host/sap/public/bc/icons 3. Menu >> Service/Host 4. Activate Object S_ICF_ADM Object class AAAB Activity 07 ICF: Name of Virtual Host ' ' ICF: GUID of ICF Service/Alias 000000000000000000000000 ICF: Service/Host/Alias NODE | validate | complete | validate | complete | validate |  | validate | complete | validate |  | validate |  | validate |  | validate |  | validate |  | validate |  | validate |  | validate
6 | Karen Nolet | HR | SE38 | Yes | N/A | N/A |  | Scramble HR data before system is open to others for validation | No | n/a | No | n/a | Yes |  | No | n/a | Yes |  | No | N/A | No | n/a | n/a | n/a | No | N/A | No | N/A | Yes |  | No | N/A |  | Do not scramble any environment without confirmation from SP PM
7 | Lucia Ma | MM | OMJ3 | Yes | Yes | Yes | Z_OMJ3 | Ensure Inventory printers are not directed to the production environment. Go to IMG: Materials management -> Inventory management and physical inventory -> Output determination -> Printer determination -> Printer determination by plant/storage location. (T_code: OMJ3) Change printers to MRP5. | Yes | complete | No | n/a | Yes |  | No | n/a | Yes |  | Yes |  | No | n/a | n/a | n/a | Yes |  | Yes |  | Yes |  | Yes
8 | Lucia Ma | MM | SPRO or SM30 (V_024_N) | Yes | Yes | Yes |  | Ensure Purchasing Group printers are not directed to the production environment. Go to IMG: Materials management -> Purchasing -> Messages ->Assign Output Devices to Purchasing Group. Change printers to MRP5. | Yes | complete | No | n/a | Yes |  | No | n/a | Yes |  | Yes |  | No | n/a | n/a | n/a | Yes |  | Yes |  | Yes |  | Yes
9 | Lucia Ma | MM | SM30 | Yes | Yes | Yes |  | Ensure ISP printouts are not directed to the production environment. Transaction SM30. Table: ZISPREQ Hit maintain and change printers to MRP5. (Also userid & password in table ZCAPARM) check view (ZV_MT*) | Yes | complete | No | n/a | Yes |  | No | n/a | Yes |  | Yes |  | No | n/a | n/a | n/a | Yes |  | Yes |  | Yes |  | Yes
10 | Lucia Ma | Classification | CT04 |  |  |  | Z#GL:CT04 | Change Facilities IO printer classification characteristic to print to spool MRP5, not a production printer. Looking for "DISTRIBUTION" | Yes | complete | No | n/a | Yes |  | No | n/a | Yes |  | Yes |  | No | n/a | n/a | n/a | Yes |  | Yes |  | Yes |  | Yes
11 | Lucia Ma | Cross App | SE38 | Yes | Yes | Yes |  | Run Program ZCOC020 | No | n/a | No | n/a | Yes |  | No | n/a | Yes |  | Yes |  | No | n/a | n/a | n/a | Yes |  | Yes |  | No | n/a | Yes
12 | Lucia Ma | Workflow | SEWTYPV |  |  |  | Z#AA:WKFLADM | Reactivate all workflow event linkages. (Tcode: SWETYPV) | validate | complete | validate | complete | Yes |  | validate | complete | validate |  | No: Yes; No: validate; n/a: validate; No: Yes; No: Yes; Yes: validate |  | Yes
13 | Lucia Ma | Email Notification | SM30 |  |  |  | Z#EM:02_ZEM0 | Update ZEHCAT table to allow e-mail messages to be sent for commitment posting errors (first time entry into ZEHCAT) also make sure "FA" ~ "FZ" are redirected. Also check EL email redirection (ZHR_EMAIL_AREA, ZHR_EMAIL_PROC which email area 'LSO') | validate | complete | No | n/a | Yes |  | No | n/a | validate |  | Yes |  | No | n/a | n/a | n/a | Yes |  | Yes |  | No | n/a | Yes
14 | Lucia Ma | CO | SE38 | Yes | Yes | Yes |  | DoF validation: Enter program GBT30FIF and search (do Find in program) for GLL. (There should be none, only GAL.) If GLL is found, then regenerate validation rules from step above. NOTE: the "30" in the program name is based on the client in which the program is run, i.e. change to "25" if the client is 025, etc. Also looking for TEMP_STRUCT-SGTXT in GBT30COJ. | validate | complete | validate | complete | Yes |  | Yes | complete | validate |  | No: Yes; No: validate; n/a: validate; No: Yes; No: Yes; Yes: Yes |  | Yes
15 | Ron Parker | FI/CO | SE38 | Yes | Yes | Yes |  | Generate validations/substitutions and sets. Run program RGUGBR00 with params: *,*,xxxxxx NOTE: This step should be completed only after all transports have been applied to the system, because transports containing validation rules will overwrite and require regeneration. | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | No: Yes; No: Yes; n/a: Yes; No: Yes; No: Yes; Yes: Yes |  | Yes
16 | Lucia Ma | FI | SE38 | Yes | Yes | Yes |  | Regenerate FBV1 JV fast entry template: Run RFFAKP01 with parameters program = SAPLF040, application = PRPOS | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | No: Yes; No: Yes; n/a: Yes; No: Yes; No: Yes; Yes: Yes |  | Yes
17 | Lucia Ma | CO user exits | CMOD | Yes | Yes | Yes |  | Enter projects COOPA003, COOMKS01, WBSENHA, CATS0002 select "components" with "change" mode, make sure all exits are activated (green dots). If any component is not noted with a green dot, then return to CMOD screen, and deactivate, then reactivate the project, and confirm the project is activated./If deactivated, all users with CMOD need to check theirs as a follow up. | validate | complete | validate | complete | Yes |  | validate | complete | validate |  | No: Yes; No: validate; n/a: validate; No: Yes; No: Yes; Yes: validate |  | Yes
18 | Lucia Ma | CO | SE38 | Yes | Yes | Yes |  | Run programs RK811XST to convert transaction groups for CO allocations (incl. Business cycles). No parameters necessary. | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | No: Yes; No: Yes; n/a: Yes; No: Yes; No: Yes; Yes: Yes |  | Yes
19 | E. Prudden | IXOS | OAC3 | Yes | Yes | Yes | Z_OAC3 | IXOS Archive Link Setting. Transaction OAC3 Change View "Links for Content Repositories": Overview. (ALSO NEED FOR SPONSORED BILL ARCHIVE KL-10/30/03) If Ron doesn't put a value in there, don't have to modify it (look at the Cont.Rep.ID field and using the pulldown, make sure that the production values are not being referenced). | validate | complete | validate | complete | Yes |  | validate | complete | validate |  | validate |  | validate |  | n/a | n/a | Yes |  | Yes |  | Yes |  | Yes
20 | E. Prudden | LO-EDI & HR-EDI | WE20 | Yes | Yes | Yes |  | Change the Receiver Port for Outbound Parameters. Transaction WE20 (Partner Profiles). Double click on "Partner Number" then dobule click on "Outbound Parmtrs". New screen come up. Change the "Receiver Port" under "Outbound Options". To confirm, check table EDP13 (field RCVPOR). | Yes | complete | validate | complete | Yes |  | validate | complete | Yes |  | Yes |  | validate |  | n/a | n/a | Yes |  | Yes |  | Yes |  | Yes
21 | G. McGrath | HR | SM30 |  |  |  |  | Validate entries in table ZHRRETIREE_PLANS | No | n/a | No | n/a | No |  | validate | complete | validate |  | No | N/A | Yes |  | validate |  | No | N/A | No | N/A | Yes |  | No | N/A
22 | G. McGrath / R3-Admin | Payroll | Dev |  |  |  |  | Update signature on check: "Void V Void" in all testing environments via transport. SHOULD NEVER GO TO PS1. Verify by transaction SE78, table Z_TTBT (SF2K927761 HRPP: Void Signiture File) | Yes | complete | validate | complete | Yes |  | validate | complete | validate |  | No: Yes; No: validate; n/a: validate; No: Yes; No: Yes; Yes: validate |  | Yes
23 | J. Tuttle | EHS / TEM | SM37 |  |  |  | IDs: ZZEHSBTCH001 ZZHRTEMBTC01 | Set up job to create users. Program, ZPE_CREATE_USER, under the ID, ZZHRTEMBTC01 , and is triggered by event, Z_TEM_SETUP (Check it first, if not exist, need to create one) NOTE: start after event "Z_TEM_SETUP" and it's a periodic job. Also create 2 additional batch jobs ZEHS_Daily_EHS_WEB_TRAINEE_FEED & ZEHS_ROLESDB_WA_RELATS under user ZZEHSBTCH01. | Yes | complete | No | n/a | Yes |  | No | n/a | Yes |  | Yes |  | No | n/a | validate |  | Yes |  | Yes |  | Yes |  | Yes
24 | G. McGrath | Payroll | Config |  |  |  |  | If refreshing a test environment determine if the control record should be checked during payrun processing if so comment out check from schema ZINO. This setting should never be commented out in a production environment. | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes |  | Yes |  | n/a | n/a | Yes |  | Yes |  | Yes |  | Yes
25 | Bob Casey | FI | OB52 or ZFICLOSE |  |  |  | Z_CA_ZFICLOSE_POST_PER_OPN_CLO or Z#GL:OB52 or ID: ZZCAZFICLOSE | Open current FI posting period. Execute the following jobs: - OPEN NEW MONTH FOR MIT COA (USER ZZGLCLOSE001) - PCARD POSTING DATE ROLLOVER (USER ZZPRBATCH001) - SCHEDULE MANAGER VARIANT CUR (USER ZZFISCHDPC01) - RRPPERIOD FLIP (USER ZZAPBATCH001) - FLIP PERIOD ON PARKED SAJV'S (USER ZZGLCLOSE001) | Yes | complete | No | n/a | Yes |  | No | n/a | Yes |  | No: Yes; No: validate; n/a: validate; No: Yes; No: Yes; Yes: validate |  | Yes |  | Timing Issue in PS1
26 | Wai-ming Li | All | [5 empty] | Dropbox pointed to new test environment | No | n/a | No | n/a | No | n/a | No | n/a | validate |  | Yes | as needed | No | n/a | No | n/a | Yes |  | Yes |  | No | n/a | Yes
27 | G. McGrath | Payroll | SE38 |  |  |  |  | Test BSI 9.0 connection. Execute program RPUBTCU0, select BSI Version 9.0 and execute. Test OC transaction (select a pernr) and verify BSI tax calculation is generated. | Yes | complete | Yes | hold | Yes |  | Yes | complete | Yes |  | No: Yes; No: Yes; n/a: validate; No: Yes; No: Yes; Yes: Yes |  | Yes
28 | G. McGrath | Payroll | PU19 |  |  |  |  | Test ADS connection. Execute Test Run of Tax Forms for individual pernrs via transaction PU19. | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | No: Yes; No: Yes; n/a: validate; No: Yes; No: Yes; Yes: Yes |  | Yes
29 | G. McGrath | HR | SM30 |  |  |  |  | Compare Wage Type table: V_512W_O | No | n/a | Yes | complete | No |  | Yes | complete | Yes |  | No | N/A | Yes |  | validate |  | No | N/A | No | N/A | Yes |  | No | N/A
30 | Sharon DiLiberto | HR/Feed | [5 empty] | Check and verify/set ZUTARCHIVECRTL table | Yes | complete | No | n/a | Yes |  | No | n/a | No | n/a | Yes |  | No | n/a | n/a | n/a | Yes |  | Yes |  | Yes |  | Yes
31 | G. McGrath | Payroll | SM30 |  |  |  |  | Check HR Payroll constant table: V_T511P, V_T511K | No | n/a | Yes | complete | No |  | Yes | complete | Yes |  | No: Yes; No: Yes; n/a: validate; No: Yes; No: Yes; Yes: Yes |  | Yes
32 | G. McGrath | Payroll | SPRO |  |  |  |  | Check PDF Validity Date for the tax form: V_T5UX7 Forms: HR_F_W2, HR_F_W2C, HR_F_1099R, HR_F_1099RC | No | n/a | Yes | complete | No |  | Yes | complete | Yes |  | No: Yes; No: Yes; n/a: validate; No: Yes; No: Yes; Yes: Yes |  | Yes
33 | R3-ADMIN | Infra-structure | [5 empty] | Turn on the FAX Gateway | Yes | complete | validate | complete | Yes |  | validate | complete | Yes |  | No: Yes; No: validate; n/a: validate; No: Yes; No: Yes; Yes: validate |  | Yes
34 | R3-ADMIN | Infra-structure | [5 empty] | Establish target systems Operation Mode (work process distributions) | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | No: Yes; No: Yes; n/a: Yes; No: Yes; No: Yes; Yes: Yes |  | Yes
35 | BASIS | HR | PA40 |  |  |  |  | The features generation program, RPUMKG00, to activate generated programs related to HR features. | No | n/a | Yes | complete | No | n/a | Yes | complete | No | n/a | No | N/A | Yes |  | Yes |  | No | N/A | No | N/A | No | n/a | No | N/A
36 | E. Prudden | TLE EDI | SAP Instance Info |  |  |  |  | In TLE, change the "Application Server" name, the "Gateway Server Name" and the "Host Name" (this action log item is only required for the hardware renewal project) | No | n/a | No | n/a | No | n/a | validate | n/a | No | n/a | No | N/A | Yes | n/a | Yes | n/a | No | N/A | No | N/A | No | n/a | No | N/A |  | SP Proj: see cut-over plan
37 | G. McGrath | Portal | ESS/Training |  |  |  |  | Test Portal Connection | Yes | complete | Yes | complete | Yes | hold | Yes | complete | Yes |  | No: Yes; No: Yes; n/a: validate; No: Yes; No: Yes; Yes: Yes |  | Yes
38 | B. Casey | FIN |  | Yes | Yes | Yes |  | Execute Trial Balance | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | N/A | No |  | No | n/a | No |  | No | N/A | No | n/a | No | N/A
39 | E. Prudden | ECAT Pointers | [5 empty] | Switch ECAT Pointers 1) In the edi subsystem (TLE), for every one of the 50+ vendors, change 2 settings (i.e. in TLE terms, the "interchange reference" and the "application"). 2) The web team needs to change the pointer on their end for the ECAT app | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | Yes |  | No | n/a | No | n/a | Yes | pending | No | N/A | No | n/a | Yes |  |  | make the switch when we switch to the test environment
40 | J. Fragala | NRL Notifications | [5 empty] | 1. Transaction IL02 • Select all functional locations in NRL Hierarchy. • For each Functional location go to Partner screen (by clicking on partner icon) • Remove existing Partners. • Back • Save. 2. Transaction IE02 • Select all equipment assigned to functional locations in NRL hierarchy • For each equipment item go to partner screen • Remove existing partners • Back • Save 3. Check data • Transaction IE07 • Use Functional location structure selection option for equipment, multiple selection option • Select all nodes of NRL functional locations • List will reflect all equipment in NRL functional locs • In selection screen also make sure that object check box for partners is selected • Run transaction • List display will show all partners assigned to equipment assigned to NRL functional locations • Review and make sure that no one who gets emails in production will get confusion email from QA system (unless necessary for specific test) | Yes | complete | No | n/a | Yes | hold | No | n/a | Yes |  | Yes |  | No | n/a | No | n/a | Yes |  | Yes |  | Yes |  | Yes
41 | ops | Portal Connection | [5 empty] | Validate/update portal gateway connection to dev/test environment. | Yes |  | Yes |  |  |  | validate |  | validate |  | No: Yes; No: Yes; n/a: validate; No: Yes; Yes: No | n/a | Yes |  |  | SF8 Portal is currently pointing to SH2
42 | FLE Team (Bob Casey) | FI | OB52 or ZFICLOSE |  |  |  | ID: ZZCAZFICLOSE | Schedule period end closing jobs – ZFICLOSE Controlling Area SING Variant Controlling Area MIT Variant | No | n/a | No | n/a |  |  | No | n/a | No | n/a | No | N/A | No | n/a | No |  | No | N/A |  |  | No | n/a
43 | L. Kushkuley | [6 empty] | Validate/Update entries in the ZHR_SRV_LINK table | validate | complete | No | n/a |  |  | validate | complete | validate |  | No: validate; No: validate; n/a: No; No: validate; Yes: validate
44 | G. Petrowsky/R3-Admin | Infra-structure | [5 empty] | Validate daily id sync is operational ID: ZZROLESFEED Jobs: ZR3_DAILY_MOIRA_&_SAP_ID_SYNC_2 ZR3_EXTID_MAINT | Yes |  | Yes | complete |  |  | Yes |  |  |  | No: Yes; No: Yes; n/a: Yes; N/A: N/A |  |  |  |  | ensure operational when SF2 is ever refreshed
45 | Karen Nolet | HR | PA30 |  |  |  |  | Reconnect APR test IDs, R3EDUI01- R3EDUI09, to PERNRs after refresh of test systems SH1, SH2, SH3. Map infotype 0105 | No | n/a | No | n/a |  |  | No |  |  |  | No: Yes; No: validate; n/a: No; No: Yes |  |  |  |  | Assignments: 00000852 R3EDUI01 00001034 R3EDUI03 00001155 R3EDUI09 00001294 R3EDUI02 00001568 R3EDUI06 00003725 R3EDUI08 00003812 R3EDUI04 00005572 R3EDUI05 00019448 R3EDUI07 00027825 R3EDUI10
46 | Lucia Ma | EL | SM30 |  |  |  |  | Check email redirection for LSO: two tables (ZHR_EMAIL_PROC with LSO and ZEHCAT with HW) | Yes | complete | validate | complete |  |  | validate | complete |  |  | No: Yes; No: validate; n/a: No; No: Yes
47 | L. Kushkuley | HR | [5 empty] | Confirm utility (ZHR_CLEAR_NH_TILES ) associated with transports: "SF2K956088 - New hire:clear tiles; NOT FOR PS1!!" and "SF2K956162 - HR Clear tiles program: recognize not a new hire" are in refreshed environment. | No | n/a | No | n/a |  |  | No |  |  |  | No: Yes; No: No; n/a: No; No: Yes |  |  |  |  | Transport should never go to production.