This document contains the following items for use during go live weekend:

- SAP Support Pack Application Task List and Schedule

- Communication and Contact Information

  - VOICEMAIL WITH STATUS: 617-324-7468

  - CONFERENCE CALL LINE: Webex
Call-in toll number (US): 617-324-0000

Saturday Access code: 642 924 098

Sunday Access code: 648 912 074

  - At the conclusion of each task in section 1 below send email to sap-upgrade-core@mit.edu indicating completion of task

- Validation Information

- Escalation Plan

- SAP Support Pack Update Task List

|  | Date | Time | Action / Task | Person(s) Responsible |
| --- | --- | --- | --- | --- |
| Pre-Update Schedule and Processes: |  |  |  |  |
|  | Monday 12/2/13 complete | 10:30 AM | Cutover weekend planning meeting IS&T. | IS&T-SAP |
|  | complete | By 5:00 PM | Activate SAP web help content in the KB | Alison Bell |
|  | Tuesday 12/3/13 complete | 3:00 PM | Steering Committee Meeting – review cut-over plan/ Go/No-go decision – W92 | Steering Committee |
|  | complete | 4:00 PM (3+ days) 37 hours | Begin online upgrade piece of the application of Enhancement Pack(s). Run time 2 days (complete by EOD 12/5). PS1 is locked during this window (no transports can be imported – critical transports would have to wait). | R3-Admin (R. Parker) |
|  | complete | By 5:00 PM (5 Minutes) | Post messages on Atlas, SAPweb and ESS (Employee Self Service) web sites about upcoming SAP outage. (message can be found on the project wiki cut-over page) | ops (Paul Cronin) |
|  | complete | By 5:00 PM | Post message on SAPgui indicating upcoming SAP outage | R3-Admin (R. Parker) |
|  | complete | By 5:00 PM | Post message on ECAT web site about upcoming SAP outage. | VPF – Cecilia Talamantes VPF – Jeff Rosa |
|  | complete | By 5:00 PM | Email Steering Committee Go/No-go decision | Project Manager ( Frank Quern) |
|  | complete | By 5:00 PM | Send message to MIT-SAP community (including SMART) about upcoming SAP outage. (see project wiki for message draft) | Project Manager (Frank Quern) |
|  | Wednesday 12/4/13 complete | 10:30 AM- 12 PM (noon) | SAPbiz meeting to review the Production Cutover schedule and details, including action log and user support | Project Manager ( Frank Quern) |
|  | complete | 2:00 – 3:00PM | Final review all issues in RT project queue, transport list, and web components. | R3-Admin /Core Team/ABAP Team/Web-Tech/BSAs |
|  | complete | 3 – 4 PM | SAP Action log team meeting to review the Production Cutover action log. | Support Pack Action log Team |
|  | complete | 4 PM | Email ops-help with list of web application deployment requests for Friday evening. | Project Manager (Frank Quern) |
|  | complete | By EOD | Final Copy of the Production Update Schedule published and emailed. | Project Manager (Frank Quern) |
|  | Thursday 12/5/13 complete | By 4 PM | Schedule Pre & Post Trial Balance reports to be used by R3-Admin for controlled data comparisons. (Schedule date should be 12/9/2013). Notify R3-Admin (R. Parker) and PM (Frank Quern) when jobs have been scheduled. | VPF Finance (Jo Lyn Whitlock) (C. Auguste) |
|  | complete | By EOD | Shift Benefits Feed (WEEKLY SUNDAY CARRIER FEEDS OE) execution from 6 AM Sunday morning to 10 PM Sunday night using the Benefits Batch id ZZHRBENBTC01. | Admin Systems (D. Roberts via Fire Fighter) |
|  | complete | By EOD | Create New Hire notification variants for Friday & Saturday suspended runs. | Admin Systems (M. Murray via Fire Fighter) |
|  | complete | By EOD | R3-Admin email message reminding key community members of the upcoming system outage. | R3-Admin (R. Parker) |
|  | Friday 12/6/13 completed | By 12 PM (noon) (3 Hours) | Reschedule (shift) DW batch jobs to Sunday night (10PM & 12AM). | DW (E. Zhitnikov) |
|  | complete | By 2 PM | Print out Facilities work order lists as back up for Monday Morning | Facilities (L. St. Croix) |
|  | complete | By 2 PM | Print out Housing work order lists as back up for Monday Morning | Facilities (L. St. Croix) |
|  | complete | By 4:20 PM | Shift Concur outbound execution from 5:00 pm to 4:20pm | Tech Services (Wai-ming Li) |
|  | complete | By 4:30 PM | Suspend weekend MITSIS Grad Appointment Feed - On sky-app-1 under userid as_cron comment out weekend rprgapxt_new job | Enterprise Appl. Admin (K. Mullins) |
|  | complete | By 5:00 PM | Workflow and JV Validation Reports - Workflow inbox report (Henry Leung) - JV Parked Documents Report (Henry Leung) - RFPs (Cathy Cherico) | VPF (Henry Leung) (Cathy Cherico) |
|  | (facilities modernization project) complete | 6:00 PM | Upgrade SAPgui on Facilities Department desktop machines (push process) - Upgrade to SAPgui 7.30.Patch Level 5 - Adjust .ini file - email sap-upgrade-core@mit.edu when complete | Facilities (M. Sherman) |
| System Isolation: |  |  |  |  |
|  | Friday 12/5/13 complete | 4:35 PM (5 Minutes) | Stop EDI Production Jobs (5 Minutes) Will need access to logistics batch id ZZLOGISBAT01 (id needs to be converted to dialog thru the course of the implementation). - email sap-upgrade-core@mit.edu when complete | Tech Services (E. Prudden) R3-Admin (G. Petrowsky) |
|  | complete | 5 PM (15 Minutes) | Shut down EDI application server (note: email sent to EDI partners earlier in the week notifying them of the shutdown window). - Run the push POs job - Shutdown the web server - Shutdown the application server - email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (O. Wang) |
|  | complete | 5 PM | Voice message update when system goes down (617-324-7468) - email sap-upgrade-core@mit.edu when complete | Project Manager (F. Quern) |
|  | complete | 5 PM | System Downtime Message (3 Down) - email sap-upgrade-core@mit.edu when complete | R3-Admin Project Manager (F. Quern) |
|  | complete | 5 PM | Bring down application servers. Production Environment becomes unavailable to users (including SAPWeb, Self Service and ECAT). - email sap-upgrade-core@mit.edu when complete | R3-Admin |
|  | complete | 5 PM | Atlas – update banner message for outage (stronger language) indicating SAP is down SAPweb/SAPwebSS Disable Gateways: Enable “PS1 System Unavailable” redirect on SAPweb & Self Service web sites (including EHS specific message activating their manual reporting of injuries) After Gateway is disabled Remove Port References (this will be a permanent setting) - email sap-upgrade-core@mit.edu when complete | Ops (Kevin Mullins) |
|  | complete | 5 PM (5 Minutes) | Suspend Drop-box processing. - email sap-upgrade-core@mit.edu when complete | Tech Services (Wai-ming Li) |
|  | complete | 5 – 7 PM | Validation Reports (Trial Balance) executed in SAP. - Ron notifies Jo Lyn Whitlock, Clarel Auguste via email cc fquern@mit.edu, rcasey@mit.edu, keyurpb@mit.edu that the reports are completed & downloaded. - VPF confirms the receipt of the Trial Balance Report. - email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF (Clarel Auguste) (Jo Lyn Whitlock) |
|  | complete | 5 – 7 PM | Limited activity in PS1. - With the exception of the Data warehouse jobs (and the trial balances) shift the remaining time-scheduled non-infrastructure jobs to execute after the weekend cutover activities (after 6am on Monday - Users locked - Save WT info to internal SAP table - email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) (G. Petrowsky) |
|  | complete | 6:00 PM | Deploy non-PM web apps (refer to deployment ticket request from Wednesday) - email sap-upgrade-core@mit.edu when complete | Ops (Paul Cronin) |
|  | (facilities modernization project) complete | 6:00 PM | Deploy PM web apps (refer to deployment ticket request from Wednesday) - email sap-upgrade-core@mit.edu when complete | Ops (Brian Knoll) |
|  | complete | 6:00 PM | Deploy javascript kb redirect mapping files (refer to deployment ticket request from Wednesday) - email sap-upgrade-core@mit.edu when complete | Ops (Paul Cronin) |
| Support Pack Application and Processes: |  |  |  |  |
|  | Friday 12/6/13 complete | 7:00 PM – 1:00 AM | Backup PS1. - Shutdown SAP System (Ron) - Split off (disable) SRDF mirror (Matt) - Bring up SAP database - Generate full (level 0) SAP database RMAN backup (Matt) - Bring up SAP (Ron) - email sap-upgrade-core@mit.edu when complete (Ron) | R3-Admin (R. Parker) OIS/Enterprise Storage & Backup (Matt Anctil) |
|  | Saturday (morning) 12/7/13 complete | 1:00 AM – 9:00 AM | SAP ERP: Execute support pack application. - Upgrade DOWN-TIME Phase - Upgrade Post Processing Phase - Email Notification to sap-upgrade-core@mit.edu from Ron Parker at the start of the support pack application - Email notifications to sap-upgrade-core@mit.edu by 12:00 midnight on Friday (12/6) with status and by 7 am on Saturday (12/8) from Ron Parker upon completion. | R3-Admin (R. Parker) |
|  | Saturday 12/7/2013 complete | 9:00 AM – 11:00 AM | GRC Upgrade - email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) |
|  | complete | 11:00 AM – 5:00 PM | Portal Upgrade (see portal task list on project wiki) Post upgrade: 1. Import Portal Transport LS#255812 Theme Changes (see attached snapshot for further info). 2. Manually make theme changes. - email sap-upgrade-core@mit.edu when complete | R3-Admin (Q. Kang) |
|  | complete | By 4:00 PM By 5:00 PM | BSI Upgrade (can occur any time after 5pm Friday) - email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) |
|  | complete | 10:00 AM – 4:00 PM Concurrent w/ following Task 44 | Backup System (RMAN) - Generate full (level 0) SAP database RMAN backup (Matt) - email sap-upgrade-core@mit.edu when complete (Matt or Ron) | R3-Admin OIS/Enterprise Storage & Backup (Matt Anctil) |
|  | complete | 10:00 AM – 6:00 PM | Execute concurrently: Generate DB Statistics (6 – 8 hours) ABAP Loads (5 hours) - email sap-upgrade-core@mit.edu when complete | R3-Admin |
|  | complete | 4 PM | Conference Call Check-in Core Team Check in at 4pm on Saturday (use conference call webex line) | Project Manager (Frank Quern) |
|  | complete | 6:30 PM (15 mins) | Restore WT Table (once loads are done) - email sap-upgrade-core@mit.edu when complete | R3-Admin |
|  | complete | 7:00 PM – 9:00 PM | Transports Application – after the completion of the ABAP Loads - Email before transport application - Email after transport application is done Included in this year’s application DSM: Import the transports as part of the step above with unconditional mode 12468. Generate transport specific ABAP loads and DSM Object Classes. Run DSM Optimization Programs | R3-Admin |
|  | complete | 9:00 PM – 10:30 PM | R3-Admin Action Log Refer to R3 Action log posted on project wiki. Unique to this year’s activities: 1. Kernel location: RFC destination SERVER_EXEC needs to be adjusted, after the update, to reflect the new location of the kernel (from .../exe to .../exe/uc/linuxx86_64). - 2. ERP Portal Interface: Activate the WD_GLOBAL_PARAMETERS service to deactivate (uncheck) the Accessibility Mode (WDACCESSIBILTY) – RT#2560032 3. Non-dialog processing memory allocation needs to be increased to 10GB. The memory allocation increases will be incorporated into in the profile changes associated with the SP update for production. 4. The following SEMO services (WDapps) will need to be de-activated in SAP using transaction SICF :. 1) zpm_vc_worder_semo_create. 2) zpm_vc_worder_semo_change. 3) zpm_vc_worder_semo_display. - email sap-upgrade-core@mit.edu when complete | R3-Admin (All) |
|  | complete | 10:30 PM | Validation reports executed (trial balance reports) - R3-ADMIN notifies Clarel Auguste and Jo Lyn Whitlock via email, cc to Frank Quern as soon as the trial balance is available for review - R3-ADMIN unlock CAUGUSTE id in PS1 - email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF Finance (Clarel Auguste) |
| Post Upgrade Schedule and Processes: |  |  |  |  |
|  | Sunday 12/8/13 complete | 1:30am – 7:00am | On Line back up of PS1 (RMAN). - Generate full (level 0) SAP database RMAN backup (Matt) - Resume hourly RMAN logfile backups (Matt) | R3-Admin OIS/Enterprise Storage & Backup (Matt Anctil) |
|  | complete | 7 – 8 am | R3-Admin Action Log continuation (as needed) Refer to R3 Action log posted on project wiki. - email sap-upgrade-core@mit.edu when complete | R3-Admin (All) |
|  | complete | 8 – 9 am | TB Validation reports validated - Clarel notifies Frank Quern when validation of the trial balance report is complete. | VPF Finance (Clarel Auguste) |
|  | (facilities modernization project) Complete | 7 – 8 am | GuiXT Setup - RFC user setup - Validate scripts - Release functions (SMFW) - Assign roles - email sap-upgrade-core@mit.edu when complete | Tech Services (S. DiLiberto) R3-Admin (G. Petrowsky) (R. Parker) |
|  | (facilities modernization project) compete | 8:00 am | Unlock PM project user ids - email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) |
|  | (facilities modernization project) complete | 8:00 am | Confirm PM Notification emails are being intercepted (redirect setting in ZEHCAT for PM Notifications). | Sharon Diliberto |
|  | (facilities modernization project) complete | 8 – 8:30 am | Execute PM pre-conversion open order report - email sap-upgrade-core@mit.edu when complete | Jim Fragala |
|  | (facilities modernization project) complete | 8:30 am – 2:00 pm | Execute PM open order conversion - email sap-upgrade-core@mit.edu when complete | Jim Fragala |
|  | (facilities modernization project) complete | 2:00 – 3:00 pm | Execute post conversion open order report - email sap-upgrade-core@mit.edu when complete | Jim Fragala |
|  | (facilities modernization project) complete | 3:00 – 4:00 pm | Facilities modernization validation - email sap-upgrade-core@mit.edu when complete | Jim Fragala |
|  | (facilities modernization project) complete | 4:00 PM | Reset ZEHCAT table setting to send emails for PM notifications. | Sharon Diliberto |
|  | complete | 8 AM | Unlock ops web-services ids in Production kmullins (Kevin Mullins) croninp (Paul Cronin) owang (Olivia Wang) . - email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) |
|  | complete | 8 AM | Enable Gateways (SAPWeb/ESS); after verifying application connections. - email sap-upgrade-core@mit.edu when complete | Ops-help (Kevin Mullins) |
|  | complete | 8:00 AM – 10:00 AM | - ADMIN SYS Action Log users unlocked - ADMIN SYS executes the PS1 Action Log / Validations and email steps completed to rest of the team (sap-action-log-team@mit.edu) - ADMIN SYS Extended Team reviews transport logs - email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) Action Log (Frank Quern) |
|  | complete | By 8 AM | EDI Step 1 Once given the go ahead from PM: Turn on the EDI “gourmet-1” server (start EDI; but do not send or push any files yet) - email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (Olivia Wang) |
|  | complete | By 8 AM | EDI (TLE) Step 2 Update SAP EDI Version number (change version # from 7.31 to 7.40) - email sap-upgrade-core@mit.edu when complete | Tech Services (E. Prudden) |
|  | complete | 8:30 AM | EDI Step 3 Start EDI Jobs (start sending EDI files) - email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (Olivia Wang) |
|  | complete | By 9 AM (5 Minutes) | EDI Step 4 (last step) Schedule EDI Job - Unlock ids - Schedule EDI Job - Monitor first job released (on the ½ hr) - email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) Tech Services (E. Prudden) (ZZLOGISBAT01) |
|  | complete | By 9 AM | EDI Step 5 (2013 only) Save port - email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) |
|  | complete | By 10 AM | Email to ist-sap@mit.edu - List of transports applied and any related issues. - List of jobs shifted in PS1 during cutover | R3-Admin (R. Parker) |
|  | complete | 10:00 AM – 11:00 AM | - Unlock KB validators - KB redirect validation - email sap-upgrade-core@mit.edu when complete | R3-Admin (G.Petrowsky) Alison Bell Lisa Robinson |
|  | complete | By 12 PM | Unlock validators (testers) - email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) |
|  | complete | By 12 PM | Update voice message whether or not Data Validation is on schedule. Email to SAP-Validation-team@mit.edu that the validation is to start on schedule | Project Manager (Frank Quern) |
|  | complete | 12 PM – 2 PM | PS1 Data Validations & Transaction processing listed in section 3 below performed by designated users; Atlas, SAPWeb and Self Service will be available for validation; All servers will be available. | BPOs Admin Sys BAs |
|  | complete | By 2 PM | Coordinators for each area should send email to sap-validation-team@mit.edu at the completion of validations indicating any issues encountered. | BPOs Admin Sys BAs R3-Admin |
|  | (facilities modernization project) complete | 2:00 PM | Move Facilities redirects into place on SAPweb. - email sap-upgrade-core@mit.edu when complete | Ops (K. Mullins) |
|  | (facilities modernization project) complete | 2:00 PM | Deactivate building_services java app on insideMIT. - email sap-upgrade-core@mit.edu when complete | Ops (K. Mullins) |
|  | complete | 4:00 PM | Conference Call Check-in Go/No Go conference call Sunday webex Line (Process owners, B. Dahlstrom, R. Parker, Wai-ming Li Admin Sys Team Leads) | Business Owners/ Test Coordinators Sponsor (B. Dahlstrom) Tech Services (W. Li) Admin Sys Team Leads IS&T Test Coordinators (K. Levie), (D. Roberts) |
|  | complete | After conf call | Send e-mail to (sapbiz, sap-upgrade-core, ist-sap@mit.edu,warehouse@mit.edu, Elena@mit.edu,) indicating decisions/results. | Project Manager (Frank Quern) |
|  | complete | 4:30 PM – 6:30 PM | Unlock users (Facilities, SMART) Unlock all users Switch the following batch ids to non-dialog: ZZLOGISBAT01 (R3-Admin notifies operations center at 3-1500). At end of unlock send message to ops-help@mit.edu, with a copy to ist-sap@mit.edu, update gateway messages. | R3-Admin (G. Petrowsky) |
|  | complete | 6:30 PM Sunday (5 Minutes) | Enable Drop box - email sap-upgrade-core@mit.edu when complete | Tech Services (Wai-ming Li) |
|  | complete | 6:30 PM | Reinstate weekend MITSIS Grad Appointment Feed - email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (K. Mullins) |
|  | complete | By 6:30 PM | Execute ProCard from Bank of America Feed - email sap-upgrade-core@mit.edu when complete | Tech Services (Eping Wei) |
|  | complete | 8PM – 12AM | Data Warehouse Job Validation - Elena confirm job validation completion via email to sap-upgrade-core@mit.edu - Run extracts (10PM & 12AM) | DW (E. Zhitnikov) |
|  | Monday 12/9/13 complete | 1:30 AM | On Line back up of PS1 (RMAN). - Generate incremental SAP database RMAN backup (Matt) - Resume daily incremental and weekly full RMAN backup schedule (Matt) | R3-Admin (R. Parker) OIS/Enterprise Storage & Backup (Matt Anctil) |
|  | complete | By 6 AM | Update the 3-down web page & SAPgui message. - email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) Project Manager (Frank Quern) |
|  | complete | By 6 AM | Remove SAP outage message on ECAT webpage. | VPF – Cecelia Talamantes VPF – Jeff Rosa |
|  | complete | By 6 AM | Remove Atlas, SAPweb, ESS and EHS messages. - email sap-upgrade-core@mit.edu when complete | Ops (K.Mullins) |
|  | complete | By 6 AM | Validate Atlas, SAPweb, ESS and EHS messages have been removed (verify in IE, Firefox, Safari) | Admin Systems (Team) |
|  | complete | 6 AM | Email notification to the MIT Community stating the update is completed and Production is available. | Project Manager (Frank Quern) |
|  | (facilities modernization project) complete | 9 AM ++ | Upgrade SAPgui on Housing Department desktop machines (manual process) - Upgrade to SAPgui 7.30.Patch Level 5 - Adjust .ini file - email sap-upgrade-core@mit.edu when complete | Facilities (M. Sherman) |
|  | complete | By 10 AM | Manually execute ZHR_NEWHIRE_NOTIFICATION with custom variants for Friday and Saturday through Batch ID. - email sap-upgrade-core@mit.edu when complete | Admin System Desiree Roberts |
|  | Tuesday 12/10/13 complete | 5 PM | Reestablish SAP Production System SRDF replication between OC11 and E40 (Matt) | OIS/Enterprise Storage & Backup |

- Communication and Contact Information

An IS&T telephone number (617-324-7468) will carry a message as to the status of the upgrade beginning at noon on Friday 12/6 through noon on Monday 12/9.  The Project Manager will update this message as needed.  A conference call number (webex) is available for check-ins during the weekend and for the Go/No Go call at 4:00pm on Sunday.

Coordinators for the weekend’s activities are listed below.

  - IS&T is responsible for:

    - System update

    - Action log execution and coordination

    - User support during production validation

    - Communication via voice message, email and conference call as to whether the update is proceeding as scheduled

    - Resolve and escalate issues where needed

  - Business area validation coordinators are responsible for

    - Coordination of production validation

    - Notify PM & Functional BSA immediately if any issues are found

    - Update PM when production validation is completed

Weekend Coordinators / Validation List / Escalation Team contact information:

| Area | Name – Location | Contact Telephone # | Email |
| --- | --- | --- | --- |
| A/P | John Larkin – NE49 | 617-253-2729 | jlarkin@mit.edu |
| VPF | Jo Lyn Whitlock – NE49 | 617-253-2771 | jolyn@mit.edu |
| VPF | Clarel Auguste – NE49 | 617-253-8488 | cauguste@mit.edu |
| VPF | Henry Leung – NE49 | 617-253-2785 | heleung@mit.edu |
| VPF | Mirella Villa – NE49 | 617-324-8455 | mirellav@mit.edu |
| VPF – Travel | Kara Sechrist – Off Campus | Contact PM | sechrist@mit.edu |
| Dept. of Facilities | Lisa St. Croix – Off Campus | Contact PM | lstcroix@plant.mit.edu |
| Dept. of Facilities | Steve Fosher – Off Campus | Contact PM | snfosh22@mit.edu |
| EHS | Laurie Veal – Off Campus | Contact PM | veal@mit.edu |
| EHS | Lee Collier – W92 | 617-324-5957 | lcollier@mit.edu |
| EHS | Joe MacLeod | Contact PM | jmacleod@mit.edu |
| HR/Benefits | Michael Peretti – Off Campus | Contact PM | mperetti@mit.edu |
| HR/Benefits | Diane Johnston – Off Campus | Contact PM | djohnsto@mit.edu |
| HR/Benefits | Riley Hart – Off Campus | Contact PM | rileyh@mit.edu |
| EL | Melissa Kavlakli – Off Campus | Contact PM | mjpotter@mit.edu |
| EL | Jane White – Off Campus | Contact PM | jwc@mit.edu |
| Procurement | Scott Ball | Contact PM | sc16196@mit.edu |
| Procurement | Cecilia Talamates – Off Campus | Contact PM | cctala@mit.edu |
| Procurement | Jeff Rosa – Off Campus | Contact PM | jrosa@mit.edu |
| Procurement | Kimberly Harmon – Off Campus | Contact PM | kharmon@mit.edu |
| VPF – HR/Payroll | Leslie Wright – NE49 | 617-253-7715 | lesliem@mit.edu |
| VPF – HR/Payroll | Darren Scartissi | Contact PM | darrenjs@mit.edu (will use batch id ZZHRLLFEED01 as part of validations?) |
| VPF – HR/Payroll | Kristen McCormick | Contact PM | cassidyk@mit.edu |
| VPF – HR/Payroll | Nicole Valente | Contact PM | nferrant@mit.edu |
| VPF – HR/Payroll | Lilian Garcia | Contact PM | llg@mit.edu |
| VPF – HR/Payroll | Tricia Sullivan-Mullen – NE49 | 617-253-4809 | tsmullen@mit.edu |
| IS&T – QA | Don Flanders – W92 | Refer to online directory | dflanders@mit.edu |
| IS&T - QA | Jack Kelliher | Contact PM | jackkell@mit.edu |
| IS&T - R3-Admin | George Petrowsky – W92 | Refer to online directory | georgep@mit.edu |
| IS&T - R3-Admin | Ron Parker – W92 | Refer to online directory | rep@mit.edu |
| IS&T - ERP System Manager | Bart Dahlstrom – W92 | Refer to online directory | bartd@mit.edu |
| IS&T - FI / EHS team lead | Siobhan Cunningham – W92 | Refer to online directory | snc@mit.edu |
| IS&T – Logistics | Adina Ion – W92 | Refer to online directory | aion@mit.edu |
| IS&T - FI Team | Bob Casey – NE49 | Refer to online directory | rcasey@mit.edu |
| IS&T - FI Team | Keyur Patel – W92 | Refer to online directory | keyurpb@mit.edu |
| IS&T – EHS/Parking | Lee Collier – W92 | Refer to online directory | lcollier@mit.edu |
| IS&T – PM/VPIS Parking | Rita Zhovnirovsky – W92 | Refer to online directory | mzhovnir@mit.edu |
| IS&T – PM | Jim Fragala – W92 | Refer to online directory | ja17661@mit.edu |
| IS&T – Log/FIN/EHS Team Coordinator | Ken Levie – W92 | Refer to online directory | khann@mit.edu |
| IS&T – Ops | Kevin Mullins – Off Campus | Refer to online directory | kmullins@mit.edu |
| IS&T – Ops | Paul Cronin – Off Campus | Refer to online directory | croninp@mit.edu |
| IS&T – Tech Services | Wai-ming Li – W92 | Refer to online directory | waiming@mit.eu |
| IS&T – Ops | Olivia Wang – W91 | Refer to online directory | owang@mit.edu |
| IS&T - Data warehouse | Elena Zhitnikov – W92 | Refer to online directory | elena@mit.edu |
| IS&T - Data warehouse | Svetlana Lemeshov – W92 | Refer to online directory | lemeshov@mit.edu |
| IS&T - HR team lead | Frank Quern – W92 | Refer to online directory | fquern@mit.edu |
| IS&T – HR/Payroll Coordinator | Desiree Roberts – W92 | Refer to online directory | robertsd@mit.edu |
| IS&T – OIS | Matt Anctil | 617-909-7889 | manctil@mit.edu |
| IS&T – OIS | Dave Kalenderian | 617-549-6991 | davek@mit.edu |
| IS&T – OIS | Garry Zacheiss | 617-216-1541 | zacheiss@mit.edu |
| IS&T - OIS | Server Operations | 617-775-3302 | Team Line |
| Project Manager | Frank Quern | 617-452-4512 | fquern@mit.edu |

Business process owners / weekend coordinators are highlighted in the above list.

Monday Morning Coverage (12/9/2013)

| Area | Name | Location | Time | Email |
| --- | --- | --- | --- | --- |
| FLE | Lee Collier | W92 | 7:30am | lcollier@mit.edu |
| FLE | Jim Fragala | W92 | 7:30am | ja17661@mit.edu |
| HRP | Cindy DeSimone | W92 | 7:30am | cindyo@mit.edu |
| HRP | Desiree Roberts | Off Campus | 7:30am | robertsd@mit.edu |
| R3-Admin | R3 Team | W92 | 7:30am | r3-admin@mit.edu |
| Tech Services | Elda Prudden | W92 | 7:30am | eprudden@mit.edu |
| Tech Services | Mark Prudden | W92 | 7:30am | mprudden@mit.edu |
| Tech Services | Carolyn Fuller | Off Campus | 7:30am | fuller@mit.edu |
| SP Project | Frank Quern | W92 | 7:30am | fquern@mit.edu |
| FLE | Admin Systems Team | W92 | 8:00am + | administrative-systems@mit.edu |
| HRP | Admin Systems Team | W92 | 8:00am + | hrpay-sppt@mit.edu |

Production Validation Information

Production Validation will occur in NE49, W92 and remotely.  Validation is scheduled to start at 2:00 PM, however, please check the message line (617-324-7468) before coming into the office or starting to test remotely.  The message will be updated by 11:30 AM if there are potential delays and by 12:00 PM if testing can start.  Please forward all validation test results, positive or negative, to the email list sap-validation-team@mit.edu as soon as your validation steps are complete.

Frank Quern will coordinate between IS&T and Business Process Owners (VPF, HR, Facilities, Payroll, EHS), on Sunday December 8th.  Frank will be responsible for the following activities:

  - Coordinating telephone message, emails with changes / updates

  - Escalating issues

  - Communicating validation results

  - Contacting R3-Admin at the conclusion of the validation to continue the system preparation for Monday

| Transaction Information | Description | Person(s) Responsible |
| --- | --- | --- |
| Trial Balance Report validation occurs first. Ron Parker will email Clarel Auguste, Jo Lyn Whitlock, and Frank Quern when the reports have finished processing. Clarel will notify Frank via telephone/email when validation is complete (Sunday morning). Frank will follow up with an email to the following: Sap-action-log-team@mit.edu, sap-upgrade-core@mit.edu |  |  |
| Report Testing | Run a trial balance | R3-Admin/Clarel Auguste |
| IS&T executes the PS1 section of the action log second. Each IS&T team member will notify the action log team when his/her steps are complete. Frank will follow up with an email to the following lists when action log is complete. Sap-validation-team@mit.edu, sap-upgrade-core@mit.edu |  |  |
| IS&T Action Log |  | Admin Systems/Tech Services |

| Transaction | Description | Tester name/ID |
| --- | --- | --- |
| The noted individuals will test/validate the following transactions. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu |  |  |
| Transaction | Description | Tester name/ID |
| SAP GUI/Atlas | Refer to FLE validation plan on project wiki’s cut-over page |  |
| SAP GUI/ESS/EL | Refer to HRP validation plan on project wiki’s cut-over page |  |

- Escalation Plan

If an issue is found, please contact Frank Quern AND the Escalation Support Team person for your area immediately.  The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall.  If the problem cannot be resolved quickly, the Business Owners will provide details related to the impact of the issue on the process and users. Bart will consider impacts for all areas as a whole and determine whether to go ahead with the update or roll back the system.

All people listed below must ensure that they can be reached on Sunday December 8th.

Functional Malfunction(s)

Jo Lyn Whitlock	Business Process Owner (VPF FAR Team)

Mike Peretti	Business Process Owner (HR) / Weekend Coordinator

Melissa Kavlakli 		Business Process Owner (EL) / Weekend Coordinator

Leslie Wright	Business Process Owner (Payroll) / Weekend Coordinator

Lisa St. Croix	Business Process Owner (Facilities) / Weekend Coordinator

Laurie Veal	Business Process Owner (EH&S) / Weekend Coordinator

Scott Ball	Business Process Owner (Procurement) / Weekend Coordinator

John Larkin	Business Process Owner (Accounts Payable) / Weekend Coordinator

Catastrophic Malfunction

Bart Dahlstrom	Project Sponsor IS&T / ADMIN SYS ERP Systems Manager

Steering Committee (+)

- Bill VanSchalkwyk 	Managing Director, EHS Programs

- Tricia Sullivan-Mullen	VPF Director of Financial Systems and Data

- Marty Dugal 		Assistant Director, Facilities Operations

- Kathleen Flynn 		HR Manager of Operations

- Frank Quern		SP Project Manager

Escalation Support Team

Ron Parker	Basis / Technical Support

George Petrowsky	R3 Authorizations

Elena Zhitnikov		Data Warehouse Team

Frank Quern	Support Pack PM

Siobhan Cunningham	FIN/LOG/EH&S Team Lead

Kevin Mullins	Ops

Wai-ming Li	Tech Services

Ken Levie	FI/LOG/EHS Team Coordinator

Desiree Roberts	HR/Payroll/EL Team Coordinator

Mailing Lists

The following email lists have been maintained for this project.

| sap-action-log-team@mit.edu | All persons having a task on the ADMIN SYS action log plus Support Pack Core Team members |
| --- | --- |
| sap-validation-team@mit.edu | All members of validation team plus all members of escalation team |
| sap-upgrade-core@mit.edu | Support Pack Core Team members |
| sap-upgrade-steering-committee@mit.edu | Steering Committee members |
| ist-sap@mit.edu | All members of the IS&T Support Pack Extended Team |