## Total ERP
Transport | Owner | SF2 Date | SF2 Time | SH2 Date | SH2 Time | Description | ZUTREQ | SP RT Ticket | Responsible Person | Comment
SF3K904024 | REP | 2013-10-23 | 10:49 | 2013-11-02 | 17:30 | R3ADM* PostUpdate SPAU Note 1876039 Adjusted - USMM Id 7554 | na | na | Ron Parker | Post-Import SPAU/SE95 SAP Note Reset Transports
SF3K904028 | REP | 2013-10-23 | 10:54 | 2013-11-02 | 17:36 | R3ADM* PostUpdate SPAU SAP Note Resets | na | na | Ron Parker | Post-Import SPAU/SE95 SAP Note Reset Transports
SF3K904032 | REP | 2013-10-23 | 10:58 | 2013-11-02 | 17:40 | R3ADM* PostUpdate SPAU SAP Note 1789868 -Reset | na | na | Ron Parker | Post-Import SPAU/SE95 SAP Note Reset Transports
SF3K904050 | REP | 2013-10-23 | 10:59 | 2013-11-02 | 17:40 | R3ADM* PostUpdate SPAU Adjustments | na | na | Ron Parker | Post-Import SPAU/SE95 SAP Note Reset Transports
SF3K904052 | REP | 2013-10-23 | 11:00 | 2013-11-02 | 17:41 | R3ADM* PostUpdate SE95 (Modification Browser) Resets | na | na | Ron Parker | Post-Import SPAU/SE95 SAP Note Reset Transports
L4HK188575 | COSTARABUSKE | 2013-10-23 | 11:00 | 2013-11-02 | 17:41 | L4HK069988 : Generated test transport | na | na | Ron Parker | SAP (BSI) Tax Data Transports per SAP Note 1921509 (TUB 124)
L4HK188576 | COSTARABUSKE | 2013-10-23 | 11:00 | 2013-11-02 | 17:41 | L4HK069996 : Generated test transport | na | na | Ron Parker | SAP (BSI) Tax Data Transports per SAP Note 1921509 (TUB 124)
L4HK188577 | COSTARABUSKE | 2013-10-23 | 11:00 | 2013-11-02 | 17:41 | L4HK070011 : Generated test transport | na | na | Ron Parker | SAP (BSI) Tax Data Transports per SAP Note 1921509 (TUB 124)
L4HK188578 | COSTARABUSKE | 2013-10-23 | 11:01 | 2013-11-02 | 17:41 | L4HK069999 : Generated test transport | na | na | Ron Parker | SAP (BSI) Tax Data Transports per SAP Note 1921509 (TUB 124)
L4HK188579 | COSTARABUSKE | 2013-10-23 | 11:01 | 2013-11-02 | 17:41 | L4HK070006 : Generated test transport | na | na | Ron Parker | SAP (BSI) Tax Data Transports per SAP Note 1921509 (TUB 124)
SF3K904022 | REP | 2013-10-23 | 11:02 | 2013-11-02 | 17:41 | R3ADM* PostUpdate HELP Variant Update | na | na | Ron Parker | SAP Online Help Variant for EHP7
SF3K904030 | EPRUDDEN | 2013-10-23 | 11:03 | 2013-11-02 | 17:41 | SP2013: EPRUDDEN Mods | na | na |  | Mods
SF3K904034 | MPRUDDEN | 2013-10-23 | 11:03 | 2013-11-02 | 17:42 | 2013 Yr End Sppt Packs: ReApply mod to fn grp RHVS | na | na |  | Mods
SF3K904036 | FQUERN | 2013-10-23 | 11:03 | 2013-11-02 | 17:42 | PP: RPCMASUT_USTAX_CALC mod for suppl taxtypes mult dist cod | na | na |  | Mods
SF3K904038 | JRTUTTLE | 2013-10-23 | 11:04 | 2013-11-02 | 17:42 | SP2013: ReApply FULLER Modifications | na | na |  | Mods
SF3K904044 | RKATKOWS | 2013-10-23 | 11:07 | 2013-11-02 | 17:42 | R3ADM* OSS 1925333 - TAX: TaxCo xx with TaxAu FED and TaxTy | na | na | Ron Parker | Post-Import EHP7 Note Corrections
SF3K904058 | RKATKOWS | 2013-10-29 | 12:10 | 2013-11-02 | 17:43 | R3ADM* OSS 1876763 - S messages in ICF runtime cause dialog | 2013-11-01 | 2556306 | Meaghan Murray | Support Pack 2013 issue
SF3K904060 | REP | 2013-10-30 | 9:17 | 2013-11-02 | 17:43 | R3ADM* OSS 1451769 GOS Attachment List EHP7 Correction | 2013-11-01 | 2558151 | Cindy Desimone | Support Pack 2013 issue
SF3K904061 | REP | 2013-10-31 | 15:19 | 2013-11-02 | 17:43 | R3ADM* OSS 855959 Activation of Extension Set | 2013-11-01 | 2558777 | Lee Collier | Support Pack 2013 issue
SF3K904046 | GEORGEP | 2013-11-01 | 16:25 | 2013-11-02 | 17:43 | R3ADM* RT2564342 N#1663177 Set USR_CUST: USER_GRP_REQUIRE=NO | 2013-11-02 | 2564342 | George Petrowsky | Support Pack 2013 issue
SF3K904048 | GEORGEP | 2013-11-01 | 16:25 | 2013-11-02 | 17:43 | R3ADM* RT2564342 N#1864062 Set: PRGN_CUST BNAME_RESTRICT=NO | 2013-11-02 | 2564342 | George Petrowsky | Support Pack 2013 issue
SF2K956324 | LKUSHKUL | 2013-10-25 | 11:59 | 2013-11-02 | 17:43 | HR New Hire: RT 2437157 urgent fix for PDF & I9 report | 2013-11-01 | 2557750 | Dietrich Warner | This was a 2013 PS1 Critical (2437157) that was reproduced in SF2
SF2K956341 | GEORGEP | 2013-10-30 | 16:05 | 2013-11-02 | 17:44 | R3ADM* SAP 2013 -RT2560886 / 2437157 Stdnt Emp Issue (KLYONS | 2013-11-01 | 2560886 | George Petrowsky | This was a 2013 PS1 Critical (2437157) that was reproduced in SF2
SF2K956351 | EPRUDDEN | 2013-10-31 | 16:58 | 2013-11-02 | 17:44 | MM: RT#2563102 Fix to PO attachments | 2013-11-01 | 2563102 | Sumukhi Pyla | This was a 2013 PS1 Critical (2563026) that was reproduced in SF2
SF2K956333 | EPRUDDEN | 2013-10-28 | 14:24 | 2013-11-02 | 17:44 | CA: RT#2557074 Reference new KB help links | 2013-11-01 | 2557074 | Ken LeVie | SAPWeb Help 2013
SF2K956339 | MPRUDDEN | 2013-10-30 | 13:04 | 2013-11-02 | 17:44 | Yr End SP: Fix to issue on ESS Edu Hist Overview | 2013-11-01 | 2559750 | Meaghan Murray | Support Pack 2013 issue
SF2K956335 | LKUSHKUL | 2013-10-29 | 15:14 | 2013-11-02 | 17:44 | HR Lincoln master data feed | 2013-11-01 | 2560024 | Karen Nolet | Support Pack 2013 issue
SF2K956337 | MPRUDDEN | 2013-10-30 | 10:48 | 2013-11-02 | 17:44 | Yr End SP: Fix to user exit in HR_GET_SUBTYPE_TEXT | 2013-11-01 | 2561150 | Meaghan Murray | Support Pack 2013 issue
SF2K956320 | SSELIGMA | 2013-11-01 | 15:27 | 2013-11-02 | 17:44 | include links to local copies of MAP javascript files | 2013-11-01 | 2564402 | Frank Quern | SAPWeb Help 2013
SF2K955899 | SSELIGMA | 2013-11-01 | 15:26 | 2013-11-02 | 17:44 | Add jquery library to zsapweb | 2013-11-01 | 2564402 | Frank Quern | SAPWeb Help 2013
SF2K956312 | REP | 2013-10-23 | 4:39 | 2013-11-02 | 20:20 | R3ADM* PM: Post-EHP7 Merged Facilities Project Objects | na | DoF Bundle | Jim Fragala | Facilities Modernization 2013 Bundle (see tab SF2K956312 for list of transports)
SF2K956314 | REP | 2013-10-23 | 5:13 | 2013-11-02 | 20:30 | R3ADM* PM: Post-EHP7 Merged Facilities Project Objects | na | DoF Bundle | Jim Fragala | Facilities Modernization 2013 Bundle (see tab SF2K956314 for list of transports)
SF2K956359 | REP | 2013-11-01 | 16:47 | 2013-11-02 | 20:32 | R3ADM* PM: Post-EHP7 Merged Facilities Project Objects -Adds | na | DoF Bundle | Jim Fragala | Facilities Modernization 2013 Bundle (see tab SF2K956359 for list of transports)
SF2K956322 | JPALOMBA | 2013-11-04 | 15:11 | 2013-11-04 | 15:30 | PM: RT#2319899 Variants for Team Work Screen #5 (Deletions) | 2013-11-04 | 2319899 | Lisa J St Croix | Facilities Modernization 2013
SF2K956372 | B_MILLER | 2013-11-05 | 9:31 | 2013-11-05 | 9:31 | PM: RT#2319899 - Correct Description of Profile MITALL01 | 2013-11-05 | 2319899 | Bruce Miller | Facilities Modernization 2013
SF2K956330 | RICHAA | 2013-11-05 | 9:41 | 2013-11-05 | 9:41 | PM: RT#2319899 Changes for search, rework RFC & ESTP report | 2013-11-05 | 2319899 | Jim Fragala | Facilities Modernization 2013
SF2K956143 | GEORGEP | 2013-11-05 | 9:44 | 2013-11-05 | 9:44 | R3ADM* RT2319899 Addt'l Auths Required (NSMITH2) | 2013-11-05 | 2319899 | Nicole Smith | Facilities Modernization 2013
SF2K956345 | PACHUTA | 2013-11-05 | 9:57 | 2013-11-05 | 9:57 | PM: RT#2319899 - TeamWork - Authorization Group | 2013-11-05 | 2319899 | Joe Palomba | Facilities Modernization 2013
SF2K956347 | JRTUTTLE | 2013-11-05 | 9:58 | 2013-11-05 | 11:58 | EHS RT 2558675 Handle both old and new REP work orders | 2013-11-05 | 2558675 | Lisa J St Croix | Facilities Modernization 2013
SF2K956378 | GEORGEP | 2013-11-05 | 11:19 | 2013-11-05 | 12:01 | R3ADM* RT2319899 Addt'l Auths Required (NSMITH2) | 2013-11-05 | 2319899 | Nicole Smith | Facilities Modernization 2013
SF3K904063 | RKATKOWS | 2013-11-05 | 12:27 | 2013-11-05 | 12:27 | R3ADM* OSS 1800384 - Error:'Maintain Employee Gender. | 2013-11-05 | 2566882 | Cindy Desimone | Support Pack 2013 issue
SF2K956380 | GEORGEP | 2013-11-05 | 13:56 | 2013-11-05 | 14:40 | R3ADM* RT2556994 addt'l FAC DF auths for ALL Users (NSMITH2) | 2013-11-05 | 2556994 | Nicole Smith | Facilities Modernization 2013
SF2K956382 | B_MILLER | 2013-11-05 | 15:17 | 2013-11-05 | 16:04 | PM: RT 2319899-Remove Required Person Responsible Requiremnt | 2013-11-05 | 2319899 | Bruce Miller | Facilities Modernization 2013
SF2K956384 | B_MILLER | 2013-11-05 | 15:34 | 2013-11-05 | 16:22 | PM: RT 2319888- Change Uniformat Code D308 to D309 | 2013-11-05 | 2319888 | Bruce Miller | Facilities Modernization 2013
SF2K956396 | SSELIGMA | 2013-11-06 | 16:09 | 2013-11-06 | 16:37 | add map links to req screens | 2013-11-06 | 2564402 | Frank Quern | SAPWeb Help 2013
SF2K956388 | LMA | 2013-11-06 | 15:26 | 2013-11-06 | 16:40 | RT 2567998: Fix FMDERIVE error | 2013-11-06 | 2567998 | Bob Casey | Support Pack 2013 issue
SF2K956374 | RICHAA | 2013-11-06 | 15:10 | 2013-11-06 | 16:42 | PM: RT#2319899 Code review, Search Req & Req estmt flag | 2013-11-06 | 2319899 | Jim Fragala | Facilities Modernization 2013
SF2K956353 | EPRUDDEN | 2013-11-07 | 8:31 | 2013-11-07 | 9:49 | PM: RT#2551477 Notif Shop Papers-fix language for 'Copy' | 2013-11-07 | 2551477 | Margarita Zhovnirovsky | Facilities Modernization 2013
SF2K956398 | EPRUDDEN | 2013-11-07 | 15:02 | 2013-11-07 | 15:11 | AP: RT#2570868 ZAP_EDI_REPORT run time error | 2013-11-07 | 2570868 | Ken LeVie | Support Pack 2013 issue
SF3K904073 | RKATKOWS | 2013-11-07 | 16:07 | 2013-11-07 | 16:25 | R3ADM* OSS 1887697 - SOH: MM60 correction for auth. check. | 2013-11-07 | 2571095 | Sumukhi Pyla | Support Pack 2013 issue
SF2K956362 | LKUSHKUL | 2013-11-07 | 15:59 | 2013-11-07 | 17:24 | SP 2013 HR: utility to check for empty files | 2013-11-07 | 2564530 | Dietrich Warner | Support Pack 2013 issue
SF2K956328 | JHOSKEN | 2013-11-08 | 13:40 | 2013-11-08 | 14:52 | PM: RT#2319899 Post EhP7 Upgrade | 2013-11-08 | 2319899 | Joe Palomba | Facilities Modernization 2013
SF2K956386 | B_MILLER | 2013-11-11 | 13:58 | 2013-11-12 | 7:33 | PM: RT 2319899-Add FEA Equipment Types for CSG | 2013-11-11 | 2319899 | Bruce Miller | Facilities Modernization 2013
SF2K956410 | GEORGEP | 2013-11-12 | 13:53 | 2013-11-12 | 14:35 | R3ADM* RT2556994 Add IW32, IW33 2 auths (NSMITH2) | 2013-11-12 | 2556994 | Nicole Smith | Facilities Modernization 2013
SF2K956412 | GEORGEP | 2013-11-12 | 16:19 | 2013-11-13 | 7:13 | R3ADM* RT2556994 B_(userstat) Auths req'd (JPALOMBA,MZHOVNIR | 2013-11-12 | 2556994 | Margarita Zhovnirovsky | Facilities Modernization 2013
SF2K956408 | JHOSKEN | 2013-11-13 | 10:28 | 2013-11-13 | 12:14 | PM: RT#s 2575063 2575521 Copy TRAN to Op.; Ltext -> Email | 2013-11-13 | 2575063 & 2575521 | Joe Palomba | Facilities Modernization 2013
SF2K956418 | DILIBERT | 2013-11-13 | 14:28 | 2013-11-13 | 14:55 | guixt Facilities project | 2013-11-13 | 2319899 | Joe Palomba | Facilities Modernization 2013
SF3K904065 | RKATKOWS | 2013-11-08 | 15:46 | 2013-11-13 | 16:18 | R3ADM* OSS 1867795 - Incorrect entries in change log. | 2013-11-13 | 2563672 | Ronald E Parker | Support Pack 2013 issue
SF3K904067 | RKATKOWS | 2013-11-08 | 15:47 | 2013-11-13 | 16:21 | R3ADM* OSS 1893579 - EAM jobs is creating dumps in backend. | 2013-11-13 | 2563672 | Ronald E Parker | Support Pack 2013 issue
SF3K904069 | RKATKOWS | 2013-11-08 | 15:47 | 2013-11-13 | 16:23 | R3ADM* OSS 1930470 - EAM Log Sync Performance | 2013-11-13 | 2563672 | Ronald E Parker | Support Pack 2013 issue
SF2K956424 | JHOSKEN | 2013-11-14 | 11:12 | 2013-11-14 | 11:28 | PM: RT#2578086 TVARV Values for DOF Documents | 2013-11-14 | 2578086 | Joe Palomba | Facilities Modernization 2013
SF2K956404 | RICHAA | 2013-11-14 | 11:55 | 2013-11-14 | 12:30 | PM: RT#2319899 Equipment object list in PM & REP Shop paper | 2013-11-14 | 2319899 | Jim Fragala | Facilities Modernization 2013
SF2K956416 | MPRUDDEN | 2013-11-14 | 13:35 | 2013-11-14 | 14:04 | HR-BEN: Remove page break from Basic Life in Enrollment Form | 2013-11-14 | 2576892 | Meaghan Murray | This was a 2013 PS1 Critical (2576898) that was reproduced in SF2
E8RK900018 | EPI-USE_LABS | 2013-11-04 | 13:05 | 2013-11-14 | 15:45 | DSM 4 build 22 | 2013-11-14 | 2557591 | Frank Quern | Support Pack 2013 issue
E4RK901162 | EPI-USE_LABS | 2013-11-12 | 17:54 | 2013-11-14 | 16:19 | DSM 4: Allow Trust Relationship enabled RFC destinations | 2013-11-14 | 2557591 | Frank Quern | Support Pack 2013 issue
SF2K956422 | FULLER | 2013-11-14 | 18:01 | 2013-11-15 | 7:33 | MM: RT#2578570 Total just unblocked & undeleted line items | 2013-11-14 | 2578570 | Sumukhi Pyla | This was a 2013 PS1 Critical (2578255) that was reproduced in SF2
SF2K956440 | GEORGEP | 2013-11-15 | 12:03 | 2013-11-15 | 13:31 | R3ADM* RT2578371 -> 2577851 Add T Ob Au N001 2 NRL (MZHOVNIR | 2013-11-15 | 2578371 | Rita Zhovnirovsky | This was a 2013 PS1 Critical (2577851) that was reproduced in SF2
SF2K956434 | GEORGEP | 2013-11-15 | 9:44 | 2013-11-15 | 13:35 | R3ADM* RT2486875 -> 2319899 ALL FAC Modrniz Roles (NSMITH2) | 2013-11-15 | 2486875 | Nicole Smith | Facilities Modernization 2013
SF2K956430 | RICHAA | 2013-11-15 | 11:39 | 2013-11-15 | 15:40 | PM: RT#2319899 Problem Description on Shop Paper | 2013-11-15 | 2319899 | Margarita Zhovnirovsky | Facilities Modernization 2013
SF2K956428 | JHOSKEN | 2013-11-15 | 15:02 | 2013-11-15 | 15:43 | PM: RT#2580044 Order Dumps in SAPLCOZV on Exit | 2013-11-15 | 2580044 | Joe Palomba | Facilities Modernization 2013
SF2K956442 | JHOSKEN | 2013-11-15 | 15:05 | 2013-11-15 | 15:44 | PM: RT#2580050 Duplicate Emails from "NEW" Order | 2013-11-15 | 2580044 & 2580050 | Joe Palomba | Facilities Modernization 2013
SF2K956432 | PACHUTA | 2013-11-15 | 10:12 | 2013-11-15 | 15:47 | PM: RT#2319899 -Team Work - Fix Multi Notification Indicator | 2013-11-15 | 2319899 | Joe Palomba | Facilities Modernization 2013
SF3K904075 | RKATKOWS | 2013-11-14 | 11:57 | 2013-11-18 | 9:42 | R3ADM* OSS 1926801 - S2I: Assertion_failed in Programm SAPL | 2013-11-18 | 2572574 | Keyurbhai Patel | Support Pack 2013 issue
SF2K956357 | B_MILLER | 2013-11-01 | 10:17 | 2013-11-18 | 10:32 | PM: RT#2319899 - Code "Other" for SIGN002 | 2013-11-18 | 2319899 | Bruce Miller | Facilities Modernization 2013
SF2K956400 | EPRUDDEN | 2013-11-18 | 13:17 | 2013-11-18 | 15:02 | MM: RT#2563073 Back button not always working in webDisp Req | 2013-11-18 | 2563073 | Sumukhi Pyla | Support Pack 2013 issue
SF2K956452 | RICHAA | 2013-11-19 | 13:30 | 2013-11-19 | 14:04 | PM: RT#2319899 Shop paper adjusted field length | 2013-11-19 | 2319899 | Jim Fragala | Facilities Modernization 2013
SF3K904077 | RKATKOWS | 2013-11-19 | 16:34 | 2013-11-19 | 17:24 | R3ADM* OSS 1872223 - Correction WHERE clause CL_AUTHCHECK_SQ | 2013-11-19 | 2582530 | Sumukhi Pyla | Support Pack 2013 issue
SF2K956414 | EPRUDDEN | 2013-11-20 | 12:12 | 2013-11-20 | 14:54 | MM: RT#2584840 Change background color of WD Close PO | 2013-11-20 | 2584840 | Sumukhi Pyla | Support Pack 2013 issue
SF2K956456 | JHOSKEN | 2013-11-20 | 11:24 | 2013-11-20 | 14:57 | PM: RT#2584614 Department number not always saved | 2013-11-20 | 2584614 | Margarita Zhovnirovsky | Facilities Modernization 2013
SF3K904079 | JRTUTTLE | 2013-11-20 | 13:58 | 2013-11-21 | 10:11 | EHS RT2560703 Mod to fix SAP 2013 EH&S change to CBIH82 | 2013-11-21 | 2560703 | Lee Collier | Support Pack 2013 issue
SF2K956467 | JHOSKEN | 2013-11-21 | 9:59 | 2013-11-21 | 10:23 | PM: RT#2587326 Controlled Access Ind. not set | 2013-11-21 | 2587326 | Joe Palomba | Facilities Modernization 2013
SF3K904087 | RKATKOWS | 2013-11-21 | 13:08 | 2013-11-22 | 7:23 | R3ADM* OSS 1933973 - TemSe files have duplicated information | 2013-11-21 | 2572777 | Gregg McGrath | Support Pack 2013 issue
SF2K956473 | RICHAA | 2013-11-22 | 10:32 | 2013-11-22 | 10:52 | PM: RT#2319899 Shop paper equipment list table read changes | 2013-11-22 | 2319899 | James Fragala | Facilities Modernization 2013
SF2K956444 | LMA | 2013-11-22 | 15:49 | 2013-11-22 | 16:04 | RT 2572554: SP2013 - CO SAFO Reports from Web | 2013-11-22 | 2572554 | Keyurbhai Patel | Support Pack 2013 issue
SF2K956487 | JHOSKEN | 2013-11-25 | 14:57 | 2013-11-25 | 15:49 | PM: RT#2590913 CC & IN Long texts don't save in WO on create | 2013-11-25 | 2590913 | Joe Palomba | Facilities Modernization 2013
SF2K956463 | LMA | 2013-11-25 | 16:15 | 2013-11-26 | 7:29 | FI: RT#2585935 SAP 2013 GL46B report wrong for multiples | 2013-11-25 | 2585935 | Keyurbhai P Patel | Support Pack 2013 issue
SF2K956446 | LMA | 2013-11-25 | 16:17 | 2013-11-26 | 7:31 | RT 2585964: SP2013 - ZPPR001 "at" statement | 2013-11-25 | 2585964 | Keyurbhai P Patel | Support Pack 2013 issue
SF2K956481 | LMA | 2013-11-25 | 15:58 | 2013-11-26 | 7:34 | RT 2591916: SP2013 ZSLOAN15 (ZA24) | 2013-11-25 | 2591916 | Keyurbhai P Patel | Support Pack 2013 issue (produced a return code of 8.)
SF2K956493 | LMA | 2013-11-25 | 16:59 | 2013-11-26 | 7:36 | RT 2591916: SAP2013 ZA24 + include files | 2013-11-25 | 2591916 | Keyurbhai P Patel | Support Pack 2013 issue
SF2K956360 | GEORGEP | 2013-11-25 | 17:14 | 2013-11-26 | 7:41 | R3ADM* RT2560886 / 2437157 Fix ESS accomodate NewHire | 2013-11-25 | 2560886 | George Petrowsky (Chuck Pizzano) | This was a 2013 PS1 Critical (2437157) that was reproduced in SF2
SF2K956475 | GEORGEP | 2013-11-25 | 17:19 | 2013-11-26 | 7:44 | R3ADM* RT2560866 Fix ESS W/ NewHire & EHP7 BDC Fix (GEORGEP | 2013-11-25 | 2560886 | George Petrowsky (Chuck Pizzano) | This was a 2013 PS1 Critical (2437157) that was reproduced in SF2
SF2K956497 | RICHAA | 2013-11-26 | 9:34 | 2013-11-26 | 10:23 | PM: RT#2592593 Remove Keys from Lock | 2013-11-26 | 2592593 | James Fragala | Facilities Modernization 2013
SF2K956477 | LMA | 2013-11-26 | 9:49 | 2013-11-26 | 10:26 | RT 2588332 - ZHRASRSUM fix field-symbol used in Loop | 2013-11-26 | 2588332 | Emily Cunningham | Support Pack 2013 issue
SF2K956495 | SSELIGMA | 2013-11-26 | 10:38 | 2013-11-26 | 10:58 | Sync map files with insidemit and atlas | 2013-11-26 | 2564402 | Frank Quern | SAPWeb Help 2013
SF2K956460 | LMA | 2013-11-26 | 13:10 | 2013-11-26 | 13:30 | RT 2572535: SP2013 - ZBILL08A etc. | 2013-11-26 | 2572535 | Keyurbhai P Patel | Support Pack 2013 issue
SF2K956469 | LMA | 2013-11-26 | 13:54 | 2013-11-26 | 13:58 | RT 2572535: SP2013 - ZSB_BUDGET_REPORT | 2013-11-26 | 2572535 | Keyurbhai P Patel | Support Pack 2013 issue
SF2K956499 | GEORGEP | 2013-11-26 | 14:25 | 2013-11-26 | 16:04 | R3ADM* RT2591832 / 2588926 F001=C001, CUP Roles (MZHOVNIR | 2013-11-26 | 2591832 & 2576810 | Rita Zhovnirovsky | This was a 2013 PS1 Critical (2588926 & 2572442) that was reproduced in SF2
SF2K956426 | EPRUDDEN | 2013-11-27 | 13:23 | 2013-11-27 | 14:19 | LS: RT#2560032 Table column grouping not working | 2013-11-27 | 2560032 | Mary T Donovan | Support Pack 2013 issue
SF2K956390 | EPRUDDEN | 2013-11-27 | 13:22 | 2013-11-27 | 14:21 | LS: RT#2560032 Cosmetic issues with SAP Portal | 2013-11-27 | 2560032 | Mary T Donovan | Support Pack 2013 issue
SF2K956501 | GEORGEP | 2013-11-27 | 11:50 | 2013-11-27 | 14:23 | R3ADM* RT2593037 Add HPLT 2 AutOrg Levls (JHOSKIN, RLEONARD) | 2013-11-27 | 2593037 | Lee Collier | Facilities Modernization 2013
SF3K904092 | REP | 2013-11-29 | 6:19 | 2013-11-29 | 6:34 | R3ADM* OSS 1931491 + Prereq. Notes -Unified Rendering 740/06 | none | 2585782 | Desiree Roberts | Support Pack 2013 issue
SF2K956505 | LMA | 2013-12-01 | 21:48 | 2013-12-02 | 7:32 | RT 2591914 -ZFM8 (ZFMANAL8) issue | 2013-12-01 | 2591914 | Keyurbhai P Patel | Support Pack 2013 issue
SF2K956507 | LMA | 2013-12-01 | 22:03 | 2013-12-02 | 7:34 | RT 2591914 -ZFM8 add authoriztion group ZOPN2ALL | 2013-12-01 | 2591914 | Keyurbhai P Patel | Support Pack 2013 issue
SF2K956523 | DILIBERT | 2013-12-03 | 12:58 | 2013-12-03 | 13:21 | PM Guixt multiple order save RT2319899 | 2013-12-03 | 2319899 | Joe Palomba | Facilities Modernization 2013
SF2K956511 | RICHAA | 2013-12-03 | 15:46 | 2013-12-03 | 16:05 | PM: RT#2597121 Change settlement amt to absolute & Sort room | 2013-12-03 | 2597121 | James Fragala | Facilities Modernization 2013
SF2K956517 | EPRUDDEN | 2013-12-03 | 15:57 | 2013-12-03 | 16:07 | MM: RT#2584840 Remove icon/symbol from web Close PO | 2013-12-03 | 2584840 | Sumukhi Pyla | Support Pack 2013 issue
SF2K956503 | GEORGEP | 2013-12-04 | 10:45 | 2013-12-04 | 11:49 | R3ADM* RT2594556 Add MITID or KERBID Selection (GEORGEP) | 2013-12-04 | 2560886 | George Petrowsky (Chuck Pizzano) | This was a 2013 PS1 Critical (2437157) that was reproduced in SF2
SF2K956525 | EPRUDDEN | 2013-12-04 | 12:50 | 2013-12-04 | 13:28 | PM: RT#2319899 Cosmetic change re: operation include txt | 2013-12-04 | 2319899 | Margarita Zhovnirovsky | Facilities Modernization 2013

## SF2K956314
Transport | Owner | SF2 Date | SF2 Time | SH2 Date | SH2 Time | Description | ZUTREQ | Proj RT Ticket | Responsible Person | Comment
SF2K955560 | B_MILLER | 2013-09-23 | 14:21 | 2013-11-02 |  | PM: RT#2319899 - Define Notification Types |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955562 | B_MILLER | 2013-09-23 | 14:22 | 2013-11-02 |  | PM: RT#2319899 - Set Screen Templates forNotification Types |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955564 | B_MILLER | 2013-09-23 | 14:23 | 2013-11-02 |  | PM: RT#2319899 - Define Long Text Control-Notification Types |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955566 | B_MILLER | 2013-09-23 | 14:24 | 2013-11-02 |  | PM: RT#2319899-Set Field Selection-Notifications (Priority) |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955568 | B_MILLER | 2013-09-23 | 14:24 | 2013-11-02 |  | PM: RT#2319899-Assign Notification Types to Order Types (Y4) |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955570 | B_MILLER | 2013-09-23 | 14:25 | 2013-11-02 |  | PM: RT#2319899 - Catalogs & Profiles for Notification Type |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955572 | B_MILLER | 2013-09-23 | 14:25 | 2013-11-02 |  | PM: RT#2319899 - Define Priorities |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955574 | B_MILLER | 2013-09-23 | 14:25 | 2013-11-02 |  | PM: RT#2319899 - Assign User Status to Notification Types |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955578 | B_MILLER | 2013-09-23 | 14:25 | 2013-11-02 |  | PM: RT#2319899 - Define System Conditions |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955580 | B_MILLER | 2013-09-23 | 14:26 | 2013-11-02 |  | PM: RT#2319899 - Define User Fields (Operations) |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955582 | B_MILLER | 2013-09-23 | 14:26 | 2013-11-02 |  | PM: RT#2319899 - Screen Areas in Notification Header |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955584 | B_MILLER | 2013-09-23 | 14:26 | 2013-11-02 |  | PM: RT#2319899 - Additional Codes for Code Groups |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955653 | B_MILLER | 2013-09-23 | 14:27 | 2013-11-02 |  | PM: RT#2319899 - Hide Notification Field "Business Area" |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955758 | JHOSKEN | 2013-09-23 | 14:36 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_XAP - Cross-Application |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955774 | B_MILLER | 2013-09-23 | 14:20 | 2013-11-02 |  | PM: RT#2319899 - Settlement Rule for SAL Order |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955776 | B_MILLER | 2013-09-23 | 14:20 | 2013-11-02 |  | PM: RT#2319899 - Add Capacity Planner HSE for Housing |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955789 | RICHAA | 2013-09-23 | 14:30 | 2013-11-02 |  | PM: Notification RFC's |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955795 | JPALOMBA | 2013-09-23 | 14:31 | 2013-11-02 |  | PM: RT#2319899 Priority Code additional configuration |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955797 | JHOSKEN | 2013-09-23 | 14:36 | 2013-11-02 |  | PM: RT#2319899 CMOD Projects, INCLUDE's |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955801 | PACHUTA | 2013-09-23 | 14:28 | 2013-11-02 |  | PM: RT#2319899 - Teamwork Progress - Issues Fix |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955811 | B_MILLER | 2013-09-23 | 14:20 | 2013-11-02 |  | RT#2319899 - Correct Planner Group Entries in T024I |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955819 | B_MILLER | 2013-09-23 | 14:20 | 2013-11-02 |  | PM RT#2319899 - Change Description of Event Code V500 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955821 | B_MILLER | 2013-09-23 | 14:19 | 2013-11-02 |  | PM RT#2319899 - Update Profiles CAC001 and CAC001M |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955833 | EPRUDDEN | 2013-09-23 | 14:27 | 2013-11-02 |  | PM: RT#2319899 Work Order Shop Papers 2 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955839 | REP | 2013-09-23 | 13:46 | 2013-11-02 |  | R3ADM* PM: SE1->SF2 Consolidated Transport Objects |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955846 | EPRUDDEN | 2013-09-23 | 14:27 | 2013-11-02 |  | PM: RT#2319899 Work Order Shop Papers 3 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955850 | B_MILLER | 2013-09-23 | 14:19 | 2013-11-02 |  | PM RT#2319899 - Define Long Text Copy from Notification |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955856 | PACHUTA | 2013-09-23 | 14:29 | 2013-11-02 |  | PM: RT#2319899 - Team Work - Mass Change fixes |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955864 | DILIBERT | 2013-09-23 | 14:29 | 2013-11-02 |  | Facilities Modernization GuiXT script changes |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955868 | PACHUTA | 2013-09-23 | 14:29 | 2013-11-02 |  | PM: RT#2319899 - Team Progress - Text Changes |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955872 | RICHAA | 2013-09-23 | 14:30 | 2013-11-02 |  | PM: Notification and order reports |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955874 | JHOSKEN | 2013-09-23 | 14:35 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_WO - Work Orders |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955877 | JHOSKEN | 2013-09-23 | 14:35 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_NTF - Notifications |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955879 | JHOSKEN | 2013-09-23 | 14:32 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_WOCNV - Work Order Conversion |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955881 | JHOSKEN | 2013-09-23 | 14:36 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_PAL - Protocol & Application Log |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955885 | PACHUTA | 2013-09-23 | 14:28 | 2013-11-02 |  | PM: RT#1850129 - Key Authorizer Table Changes |  | 1850129 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955889 | B_MILLER | 2013-09-23 | 14:19 | 2013-11-02 |  | PM: RT#2319899 - Set Operation Field Key Default |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955895 | RICHAA | 2013-09-23 | 14:30 | 2013-11-02 |  | Pm: Changes to report ZPM_WOTPO |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955908 | B_MILLER | 2013-09-23 | 14:18 | 2013-11-02 |  | PM: RT#2319899 - Code Group Classification |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955914 | RICHAA | 2013-09-23 | 14:30 | 2013-11-02 |  | PM: Changes to report ZPMAGING |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955922 | JRTUTTLE | 2013-10-04 | 15:01 | 2013-11-02 |  | EHS RT 2503443 EHS-PM Integration fix Facilities Modernizatn |  | 2503443 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955954 | JPALOMBA | 2013-09-23 | 14:31 | 2013-11-02 |  | PM: RT#2319899 Variants for Team Work Screen |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955975 | JHOSKEN | 2013-09-30 | 11:45 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_WOCNV - Work Order Conversion |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955978 | RICHAA | 2013-09-25 | 15:55 | 2013-11-02 |  | PM: RT#2319899 Changes to Notification RFC's |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955982 | JHOSKEN | 2013-09-30 | 11:46 | 2013-11-02 |  | PM: RT#2319899 Standard Texts for Emails |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955986 | JHOSKEN | 2013-09-30 | 11:46 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_XAP - Cross-Application |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955990 | RICHAA | 2013-09-30 | 9:24 | 2013-11-02 |  | PM: RT#2319899 Changes to Notification RFC's & reports |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956010 | JHOSKEN | 2013-09-30 | 11:46 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_WO - Work Orders |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956012 | JHOSKEN | 2013-09-30 | 11:47 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_NTF - Notifications |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956024 | RICHAA | 2013-09-26 | 11:41 | 2013-11-02 |  | PM: RT#2319899 Status changes to ZPM_WOTPO |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956028 | DILIBERT | 2013-10-01 | 14:08 | 2013-11-02 |  | PM Guixt scripts |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956062 | JHOSKEN | 2013-09-30 | 11:48 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_PAL - Protocol & Application Log |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956066 | RICHAA | 2013-09-30 | 16:01 | 2013-11-02 |  | PM: RT#2319899 Work Order User Status Report |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956070 | EPRUDDEN | 2013-10-01 | 15:08 | 2013-11-02 |  | PM: RT#2319899 Notification Shop Papers 2 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956074 | EPRUDDEN | 2013-10-01 | 15:09 | 2013-11-02 |  | PM: RT#2319899 Work Order Shop Papers 4 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956078 | PACHUTA | 2013-10-02 | 15:58 | 2013-11-02 |  | PM: RT#2319899 - Team Progress - Fix TECO button |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956080 | B_MILLER | 2013-09-30 | 15:56 | 2013-11-02 |  | PM: RT#2319899 - Add "Codes" Tab to Notifications |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956082 | RICHAA | 2013-09-30 | 16:01 | 2013-11-02 |  | PM: RT#2319899 Authorization group ZPM_WO_OPER_USER_STATUS |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956090 | JHOSKEN | 2013-10-02 | 14:27 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_NTF - Notifications |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956092 | JHOSKEN | 2013-10-02 | 14:27 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_XAP - Cross-Application |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956094 | RICHAA | 2013-10-03 | 12:58 | 2013-11-02 |  | PM: RT#2319899 Changes to RFC |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956096 | JHOSKEN | 2013-10-02 | 14:27 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_WOCNV - Work Order Conversion |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956098 | JHOSKEN | 2013-10-02 | 14:28 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_WO - Work Orders |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956100 | EPRUDDEN | 2013-10-01 | 15:15 | 2013-11-02 |  | PM: RT#2319899 Work Order Shop Papers 5 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956102 | PACHUTA | 2013-10-02 | 15:58 | 2013-11-02 |  | PM: RT#2319899 - Team Work - Mass Change- Fix opr usr status |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956118 | EPRUDDEN | 2013-10-02 | 10:24 | 2013-11-02 |  | PM: RT#2319899 Work Order Shop Papers 6 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956121 | RICHAA | 2013-10-10 | 13:39 | 2013-11-02 |  | PM: RT#2319899 Notification and Order reports |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956135 | EPRUDDEN | 2013-10-02 | 14:57 | 2013-11-02 |  | PM: RT#2319899 Notification Shop Papers 3 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956141 | JHOSKEN | 2013-10-07 | 14:53 | 2013-11-02 |  | PM: RT#2319899 Pkgs. ZPM0_XAP, ZPM0_PAL |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956145 | JPALOMBA | 2013-10-03 | 8:02 | 2013-11-02 |  | PM: RT#2319899 Variants for Team Work Screen #2 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956149 | EPRUDDEN | 2013-10-03 | 10:07 | 2013-11-02 |  | PM: RT#2319899 Notification Shop Papers 4 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956153 | JHOSKEN | 2013-10-07 | 14:54 | 2013-11-02 |  | PM: RT#2319899 Pkgs. ZPM0_NTF, ZPM0_WO, ZPM0_WOCNV |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956159 | PACHUTA | 2013-10-07 | 12:30 | 2013-11-02 |  | PM: RT#2319899 - Team Work Screen - Fix Complete Flag |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956170 | RICHAA | 2013-10-04 | 15:04 | 2013-11-02 |  | PM: RT#2319899 TVARV variable for Operation TECO |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956172 | MZHOVNIR | 2013-10-04 | 15:28 | 2013-11-02 |  | to make person respnsbl required field in WCTR |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956176 | RICHAA | 2013-10-04 | 15:04 | 2013-11-02 |  | PM: RT#2319899 Pkg. ZPM0_WO - Work Orders |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956186 | MZHOVNIR | 2013-10-07 | 8:15 | 2013-11-02 |  | to add person responsible to the visitor parking Work Center |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956194 | RICHAA | 2013-10-10 | 13:39 | 2013-11-02 |  | PM: RT#2319899 RFC changes |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956200 | JHOSKEN | 2013-10-10 | 13:27 | 2013-11-02 |  | PM: RT#2319899 Parts of Pkgs. XAP, PAL, NTF, WO, WOCNV |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956204 | DILIBERT | 2013-10-17 | 9:20 | 2013-11-02 |  | Guixt Scripts part3 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956208 | MZHOVNIR | 2013-10-09 | 9:42 | 2013-11-02 |  | add respnsbl persn for WRKC "DLT"-tradespeople who have left |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956210 | EPRUDDEN | 2013-10-09 | 12:00 | 2013-11-02 |  | PM: RT#2319899 Work Order Shop Papers 7 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956212 | RICHAA | 2013-10-09 | 16:00 | 2013-11-02 |  | PM: RT#2319899 ZPMKEYAUTHR |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956222 | JPALOMBA | 2013-10-10 | 9:57 | 2013-11-02 |  | PM: RT#2319899 Variants for Team Work Screen #3 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956230 | B_MILLER | 2013-10-11 | 12:48 | 2013-11-02 |  | RT#2319899 - Updates to Code Groups |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956232 | RICHAA | 2013-10-11 | 12:47 | 2013-11-02 |  | PM: RT#2319899 Outside CAC locations |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956249 | PACHUTA | 2013-10-16 | 9:25 | 2013-11-02 |  | PM: RT#2319899 - Team Progress - Fix Closed Flag |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956257 | JHOSKEN | 2013-10-17 | 13:45 | 2013-11-02 |  | PM: RT#2319899 Parts of Pkgs. XAP, PAL, NTF, WO, WOCNV |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956259 | RICHAA | 2013-10-16 | 16:13 | 2013-11-02 |  | PM: RT#2319899 Repairs codegroup and Code review changes |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956263 | GEORGEP | 2013-10-18 | 7:38 | 2013-11-02 |  | R3ADM* RT252701 Menu Text Adjustments (NSMITH2) |  | 252701 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956269 | B_MILLER | 2013-10-17 | 9:28 | 2013-11-02 |  | PM: RT#2319899 - Add Restroom Repair Code Group & Codes |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956273 | B_MILLER | 2013-10-16 | 12:16 | 2013-11-02 |  | PM: RT#2319899 - Add Restroom Repair Group to Profiles |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956275 | PACHUTA | 2013-10-16 | 16:14 | 2013-11-02 |  | PM: RT#2319899 - Team Work - Mass Change - Fix Opr Work Ctr |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956279 | PACHUTA | 2013-10-17 | 13:30 | 2013-11-02 |  | PM: RT#2319899 - Team Progress - Fix Locking error in BDC |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956281 | B_MILLER | 2013-10-17 | 7:49 | 2013-11-02 |  | PM: RT#2319899 - Planner Group Description Update 20131017 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956283 | JPALOMBA | 2013-10-17 | 7:37 | 2013-11-02 |  | PM: RT#2319899 Variants for Team Work Screen #4 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956298 | JPALOMBA | 2013-10-18 | 9:03 | 2013-11-02 |  | PM: RT#2319899 Semo priority Type change |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955446 | GEORGEP | 2013-08-02 | 8:34 | 2013-11-02 |  | R3ADM* RT2453692 Add Notif, WO's Auths (MZHOVNIR) |  | 2453692 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955462 | GEORGEP | 2013-08-02 | 15:24 | 2013-11-02 |  | R3ADM* RT2453692 Adjusted Auths to be correct (MZHOVNIR) |  | 2453692 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955468 | GEORGEP | 2013-08-05 | 10:50 | 2013-11-02 |  | R3ADM* RT2453692 Add auth 4 B_USERSTAT 2 (MZHOVNIR) |  | 2453692 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955744 | GEORGEP | 2013-09-17 | 17:08 | 2013-11-02 |  | R3ADM* RT2486875 New Auth Object for FAC Modern. (NSMITH2) |  | 2486875 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955941 | GEORGEP | 2013-09-17 | 16:49 | 2013-11-02 |  | R3ADM* RT2319899 Roles for PM Modrn. Proj. (JA17661) |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K955950 | GEORGEP | 2013-09-19 | 7:13 | 2013-11-02 |  | R3ADM* RT2319899 New CONVRSN role 4 PM (NSMITH2,JPALOMBA) |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956020 | GEORGEP | 2013-09-25 | 16:21 | 2013-11-02 |  | R3ADM* RT2319899 Chg ZPMKEY04 2 ZPM00004 (MZHOVNIR) |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956114 | GEORGEP | 2013-10-02 | 10:29 | 2013-11-02 |  | R3ADM* RT2527016 Comp Role 4 House Mgr (NSMITH2) |  | 2527016 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956143 | GEORGEP | 2013-10-02 | 16:20 | 2013-11-02 |  | R3ADM* RT2319899 Addt'l Auths Required (NSMITH2) |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314
SF2K956314 | REP | 2013-10-23 | 5:13 | 2013-11-02 |  | R3ADM* PM: Post-EHP7 Merged Facilities Project Objects |  |  | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956314

## SF2K956359
Transport | Owner | E070 Date | E070 Time | SH2 Date | SH2 Time | Description | ZUTREQ | Proj RT Ticket | Responsible Person | Comment
SF2K955263 | MZHOVNIR | 2013-07-19 | 9:52 | 2013-11-02 |  | #2429587 create new User Stat profiles for Notifications |  | 2429587 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956359
SF2K955251 | MZHOVNIR | 2013-07-19 | 9:56 | 2013-11-02 |  | #2429587 create new Header & Oper User stat profiles for WOs |  | 2429587 | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956359
SF2K955338 | MZHOVNIR | 2013-07-19 | 16:12 | 2013-11-02 |  | take out secondary stats from opr user stat profile |  |  | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956359
SF2K956359 | REP | 2013-11-01 | 16:47 | 2013-11-02 |  | R3ADM* PM: Post-EHP7 Merged Facilities Project Objects -Adds |  |  | Jim Fragala | Facilities Modernization 2013 bundled in SF2K956359

## SF2K956312
Transport | Owner | E070 Date | E070 Time | SH2 Date | SH2 Time | Description | ZUTREQ | Proj RT Ticket | Responsible Person | Comment
SF2K956312 | REP | 2013-10-23 | 4:39 | 2013-11-02 |  | R3ADM* PM: Post-EHP7 Merged Facilities Project Objects |  |  | Jim Fragala | Facilities Modernization 2013 bundle SF2K956312
SF2K955817 | B_MILLER | 2013-09-10 | 17:09 | 2013-11-02 |  | RT#2319899 - Create "Location" W64 |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundle SF2K956312
SF2K955910 | GEORGEP | 2013-09-11 | 11:30 | 2013-11-02 |  | R3ADM* RT2502362 Add SO10 to role (NSMITH2, B_MILLER) |  | 2502362 | Jim Fragala | Facilities Modernization 2013 bundle SF2K956312
SF2K955943 | B_MILLER | 2013-09-20 | 11:46 | 2013-11-02 |  | RT#2319899 - Add additional SEMO Planner Groups |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundle SF2K956312
SF2K955977 | REP | 2013-09-23 | 13:39 | 2013-11-02 |  | R3ADM* PM: SE1->SF2 Consolidated Transport Objects (DTEL) |  |  | Jim Fragala | Facilities Modernization 2013 bundle SF2K956312
SF2K956018 | B_MILLER | 2013-09-25 | 14:52 | 2013-11-02 |  | PM: RT#2319899 - Long Texts for Signage Activities |  | 2319899 | Jim Fragala | Facilities Modernization 2013 bundle SF2K956312

## Portal Transport
Transport | Owner | SF2 Date | SF2 Time | SH2 Date | SH2 Time | Description | ZUTREQ | SP RT Ticket | Responsible Person | Comment
LS#255812 | EPRUDDEN | na | na | 2013-11-02 | na | Theme Changes (SAP Portal transport - see attached snapshot for further info). | na | 2557812 | Mary Donovan | Support Pack 2013 issue

## FireFigher Transports
Transport | Description
ACDK900199 | R3ADM* OSS 1821337 PostSP12-13 SPAU Adjustment
ACDK900207 | R3ADM* Post-SP SPAU Note Resets
ACDK900201 | R3ADM* OSS 702/15 I,II,III,IV,V,VI Unified Rendering Notes
ACDK900203 | R3ADM* PostSPUpdate SPAU Adjustments
ACDK900205 | R3ADM* OSS 1800347 GRAC_SPM Short Dump on FF Login
ACDK900209 | R3ADM* OSS 1867795 Incorrect change log entries for profiles
ACDK900211 | R3ADM* OSS 1893579 EAM jobs create dumps on NW740 (ERP+EHP7)
ACDK900213 | R3ADM* OSS 1930470 EAM Log Sync Performance
ACDK900215 | R3ADM* SAPGRC Workflow Prefix Customization